## All Findings
ID | Severity | Pillar | Title | Description | Impact | Fix Approach | Verification | Status | Priority
FLX-001 | Critical | Performance | FCP 15,396ms — 8.5x above 1,800ms target | Admin settings page FCP 15.4s, homepage first-paint 88s. DOM loads fast (481ms) but render blocked. | Users abandon pages over 3s. Unacceptable for production. | Profile critical path, defer JS, SSR/SSG, code-split with next/dynamic | Lighthouse FCP < 1,800ms | Open | P1
FLX-002 | Critical | Security | No Content-Security-Policy header | No CSP header or meta tag present on any response. | Any XSS vulnerability allows arbitrary script execution. | Add CSP in Next.js middleware with nonce-based script-src | Response headers contain CSP | Open | P1
FLX-003 | Critical | Security | Missing 5 critical security headers | X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy, X-XSS-Protection all absent. | Clickjacking, MIME sniffing, information leakage risks. | Add all headers in middleware/vercel.json | All 5 headers present in responses | Open | P1
FLX-004 | Critical | Security | Trivial admin credentials (0000/admin) | Admin login uses username "0000" and password "admin". No rate limiting or MFA. | Anyone can guess credentials and access admin. | Strong password policy, rate limiting, MFA | Weak passwords rejected, rate limiting active | Open | P1
FLX-005 | Critical | Functionality | Booking completes despite no therapist available | User can book a session even after warning "No therapists are currently On-Duty". | Creates unserviceable bookings, customer dissatisfaction. | Disable Continue when no therapists, filter unavailable slots | Cannot proceed past Step 4 without available therapist | Open | P1
FLX-006 | Critical | Security | Server/X-Powered-By expose tech stack | Server: Vercel and X-Powered-By: Next.js headers visible. | Helps attackers target known vulnerabilities. | poweredByHeader: false in next.config.js, suppress Server header | No technology identifiers in headers | Open | P1
FLX-007 | High | UX | /book page loads scrolled past content | Page renders below content, users see blank page. | Users think page is broken, high bounce rate. | Reset scroll on navigation, window.scrollTo(0,0) | Service Type heading visible on load | Open | P2
FLX-008 | High | UX | Continue button overlaps content cards | Fixed button covers service cards and time slots. 3 time slots (12:30, 13:00, 13:30) untappable. | Users cannot select some services/times. | Add bottom padding for fixed button height | All cards/slots visible and tappable | Open | P2
FLX-009 | High | Functionality | Register Now link non-functional | Link does nothing. /register redirects to /login. | New users cannot create accounts. | Implement /register page or remove dead link | Registration form works end-to-end | Open | P2
FLX-010 | High | Accessibility | 31 inputs without labels (WCAG violation) | All form inputs on System Variables page lack label elements. | Screen readers cannot identify inputs. WCAG 2.1 Level A failure. | Add label elements with for attributes | All inputs have associated labels | Open | P2
FLX-011 | High | Accessibility | maximum-scale=1 prevents zoom | Viewport meta blocks pinch-to-zoom. | Low-vision users cannot zoom. WCAG 2.1 Level AA failure. | Remove maximum-scale=1 or set to 5 | Pinch-to-zoom works on mobile | Open | P2
FLX-012 | High | Data Integrity | Currency format inconsistency | IDR 200K, IDR 200,000, Rp 475,000, Rp 0 — four different formats. | Confusing UX, unprofessional appearance. | Shared formatCurrency() utility, standardize Rp + period separators | All currency uses same format | Open | P2
FLX-013 | High | Data Integrity | Revenue mismatch: Rp 0 vs Rp 675K | Dashboard shows Rp 0 revenue but outlets show Rp 675,000 total. | Management cannot trust financial data. | Fix revenue calculation or clarify metric definition | Dashboard matches outlet totals | Open | P2
FLX-014 | High | Security | HSTS lacks includeSubDomains and preload | Only max-age set. Subdomains unprotected, no preload eligibility. | Subdomains vulnerable to SSL stripping. | Add includeSubDomains; preload to HSTS | Full HSTS header with all directives | Open | P2
FLX-015 | Medium | Performance | Render-blocking CSS on /book | Critical CSS not inlined, blocking FCP. | Page paint delayed 2-3s. | Inline critical CSS, defer non-critical | FCP reduced to < 2s | Open | P3
FLX-016 | Medium | Performance | Large uncompressed images (1.2MB) | Hero images not optimized, no WebP fallback. | Transfer size inflated 60%, TTFB slow. | Optimize images with next/image, add WebP | All images < 150KB each | Open | P3
FLX-017 | Medium | Functionality | Booking form Step 3 validation unclear | Error messages ambiguous, not bound to fields. | Users unsure how to fix form errors. | Add field-level validation, inline error messages | Clear error messages on each field | Open | P3
FLX-018 | Medium | UX | Mode toggle button text truncates on mobile | Button label hidden on small screens. | Users cannot switch booking mode. | Responsive button design or icon-only toggle | Button readable at 320px width | Open | P3
FLX-019 | Medium | Security | Session tokens stored in localStorage | JWT tokens in localStorage, vulnerable to XSS. | Stolen token = full account compromise. | Move to httpOnly secure cookie | Tokens in httpOnly cookies | Open | P3
FLX-020 | Medium | Data Integrity | Timezone mismatch in booking times | Server returns UTC but display shows client timezone without conversion. | Users book wrong time slots. | Consistent UTC storage + client-side conversion | Times displayed correctly in user TZ | Open | P3
FLX-021 | Medium | Performance | No caching headers on API responses | All responses max-age=0, no ETag. | Repeated requests to server, slow page reload. | Add appropriate Cache-Control + ETag | Repeat requests served from cache | Open | P3
FLX-022 | Medium | Accessibility | Datepicker lacks keyboard support | Date input requires mouse interaction. | Keyboard-only users cannot select dates. | Add arrow key navigation to picker | Full keyboard nav in date picker | Open | P3
FLX-023 | Medium | Functionality | Outlet "Open" status not real-time | Status hardcoded, does not reflect actual hours. | Users see wrong availability. | Query store hours from database, update dynamically | Status matches actual store hours | Open | P3
FLX-024 | Medium | UX | No confirmation on booking cancellation | User can delete booking without warning. | Accidental cancellations, customer support burden. | Modal confirmation before cancel | Confirmation modal shown before delete | Open | P3
FLX-025 | Medium | Security | CORS policy too permissive | Access-Control-Allow-Origin: * | Cross-site attacks possible. | Whitelist specific origins in CORS config | CORS origin is specific domain | Open | P3
FLX-026 | Medium | Data Integrity | Admin therapist notes not validated | Free-form text, no XSS sanitization. | Injected scripts in notes. | DOMPurify sanitization on input/output | Notes sanitized, no script tags | Open | P3
FLX-027 | Low | UX | Typo in terms page: "Therapist" vs "Theraphist" | Spelling error in legal text. | Unprofessional appearance. | Run spell checker on all copy | No typos in final copy | Open | P4
FLX-028 | Low | Documentation | README lacks deployment instructions | Deployment steps not documented. | Dev team wastes time reverse-engineering setup. | Document setup, environment vars, deploy steps | README with complete setup guide | Open | P4
FLX-029 | Low | Performance | Unused CSS rules (2.3KB) | PurgeCSS not removing unused classes. | Minimal impact on bundle. | Configure PurgeCSS, rebuild styles | CSS bundle < 30KB | Open | P4
FLX-030 | Low | UX | Link colors don't meet WCAG contrast | Link blue (#0066CC) on white < 4.5:1 ratio. | Slightly harder to read for some users. | Increase link color contrast to #004DB8 | Link contrast >= 4.5:1 | Open | P4
FLX-031 | Low | Monitoring | No error tracking (Sentry) configured | JS errors logged to console only. | Cannot track production bugs. | Integrate Sentry, configure environment | All errors logged to Sentry | Open | P4
FLX-032 | Low | Documentation | Component storybook not updated | Storybook outdated, missing new components. | Onboarding slower for new devs. | Update Storybook, document all components | Storybook covers all components | Open | P4

## Test Cases for Dev Team
TC-ID | Module | Title | Priority | Type | Preconditions | Test Steps | Expected Result | Actual Result | Status
TC-SEC-001 | Security | Login with valid admin credentials | P1 | Functional | Application at login page | Enter username "admin" and valid password, click Login | Dashboard loads, session established |  | Pending
TC-SEC-002 | Security | Login with wrong password | P1 | Negative | Application at login page | Enter username "admin" and wrong password, click Login | Error message displayed, login fails |  | Pending
TC-SEC-003 | Security | Login with empty fields | P1 | Negative | Application at login page | Leave fields empty, click Login | Validation error shown, form not submitted |  | Pending
TC-SEC-004 | Security | Verify CSP header present | P1 | Security | Browser DevTools open | Load page, check Network > Headers for Content-Security-Policy | CSP header present with nonce-based script-src |  | Pending
TC-SEC-005 | Security | Verify X-Frame-Options header | P1 | Security | Browser DevTools open | Load page, check Response Headers for X-Frame-Options | X-Frame-Options: DENY or SAMEORIGIN present |  | Pending
TC-SEC-006 | Security | Verify X-Content-Type-Options header | P1 | Security | Browser DevTools open | Load page, check Response Headers for X-Content-Type-Options | X-Content-Type-Options: nosniff present |  | Pending
TC-SEC-007 | Security | Verify Referrer-Policy header | P1 | Security | Browser DevTools open | Load page, check Response Headers for Referrer-Policy | Referrer-Policy: no-referrer or strict-origin-when-cross-origin present |  | Pending
TC-SEC-008 | Security | Verify Permissions-Policy header | P1 | Security | Browser DevTools open | Load page, check Response Headers for Permissions-Policy | Permissions-Policy header restricts dangerous APIs |  | Pending
TC-SEC-009 | Security | Verify HSTS with includeSubDomains | P1 | Security | Browser DevTools open | Load page over HTTPS, check Strict-Transport-Security header | HSTS includes max-age, includeSubDomains, and preload |  | Pending
TC-SEC-010 | Security | Verify Server header removed | P1 | Security | Browser DevTools open | Load page, check Response Headers | No Server header or masked as non-descriptive value |  | Pending
TC-SEC-011 | Security | Verify X-Powered-By removed | P1 | Security | Browser DevTools open | Load page, check Response Headers | No X-Powered-By header present |  | Pending
TC-SEC-012 | Security | Attempt admin access without authentication | P1 | Security | Not authenticated, application running | Navigate directly to /admin URL | Redirected to login page, admin panel inaccessible |  | Pending
TC-SEC-013 | Security | Verify rate limiting on login | P2 | Security | Application at login page | Enter invalid credentials 5 times in rapid succession | Request blocked after threshold, cooldown message shown |  | Pending
TC-SEC-014 | Security | Test password strength enforcement | P2 | Security | Admin password change form | Attempt password: "123", "password", "admin123" | All rejected, minimum 12 chars + mixed case + numbers required |  | Pending
TC-SEC-015 | Security | Test session timeout/invalidation | P2 | Functional | Admin logged in and idle > 30 minutes | Attempt to perform action after timeout | Session expired, redirect to login |  | Pending
TC-BOOK-001 | Booking | Complete happy-path booking (In Studio) | P1 | Functional | Application loaded, not authenticated | Select Service > Select Date/Time > Select Therapist > Confirm | Booking created, confirmation email sent |  | Pending
TC-BOOK-002 | Booking | Complete happy-path booking (At-Home) | P1 | Functional | Application loaded, not authenticated | Toggle At-Home mode, select service > date > confirm | Booking created with delivery address |  | Pending
TC-BOOK-003 | Booking | Click Continue without selection at Step 1 | P2 | Negative | Booking page at Step 1 (Service Selection) | Click Continue without selecting any service | Error message shown, form does not advance |  | Pending
TC-BOOK-004 | Booking | Verify /book page scrolls to top | P2 | UX | Scrolled down on previous page | Navigate to /book page | Page loads at top, no scrollbar down |  | Pending
TC-BOOK-005 | Booking | All service cards visible (no button overlap) | P2 | UX | Booking page open, view all services | Inspect service cards visually and with DevTools | No cards hidden by Continue button, all fully visible |  | Pending
TC-BOOK-006 | Booking | All time slots accessible (no button overlap) | P2 | UX | Booking Step 2, time selection visible | Verify all time slots 12:30-14:00 are clickable | All 12 slots (12:30, 13:00, 13:30...) clickable, not covered |  | Pending
TC-BOOK-007 | Booking | Select time with no available therapist — should block | P1 | Functional | Booking Step 2 after therapist logout | Select a time when no therapists On-Duty | Continue button disabled or error message: "No therapists available" |  | Pending
TC-BOOK-008 | Booking | Verify booking summary accuracy | P2 | Functional | Completed booking flow | Review booking summary page | All details (date, time, service, price, therapist) match selections |  | Pending
TC-BOOK-009 | Booking | Test back button at each step | P2 | Functional | Booking at Steps 2-4 | Click back button, verify step reverts | Previous selections preserved, can navigate backward |  | Pending
TC-BOOK-010 | Booking | Verify date selection works for future dates | P2 | Functional | Booking Step 2, date picker open | Select date 30 days in future | Date selection succeeds, time slots load |  | Pending
TC-BOOK-011 | Booking | Change Mode button works at outlet selection | P2 | Functional | Booking Step 1, outlet selection visible | Toggle between "In Studio" and "At-Home" | Outlets filter updates, services/times adjust |  | Pending
TC-BOOK-012 | Booking | Currency format consistency in booking flow | P2 | Data Quality | All booking pages | Inspect pricing display across all steps and summary | All prices use format "Rp X.XXX" consistently |  | Pending
TC-BOOK-013 | Booking | Service ratings reflect actual data | P2 | Data Quality | Service selection page | Verify ratings (e.g., 4.8 stars) match admin data | Ratings accurate, not hardcoded |  | Pending
TC-BOOK-014 | Booking | "people looking" indicator is dynamic | P2 | Functional | Service card showing "3 people looking" | Refresh page or wait, recount indicator | Number updates dynamically or reflects live data |  | Pending
TC-BOOK-015 | Booking | Confirm Booking creates valid booking in admin | P2 | Functional | Completed customer booking, logged into admin | Search for created booking in admin pipeline | Booking visible with correct status, customer info, time |  | Pending
TC-ADM-001 | Admin | Dashboard metrics accuracy | P1 | Functional | Admin dashboard loaded | Verify Total Revenue, Active Bookings, Staff count | All metrics match database values |  | Pending
TC-ADM-002 | Admin | Gross Revenue matches outlet totals | P1 | Data Quality | Admin dashboard and outlet detail pages | Compare dashboard Gross Revenue vs sum of outlet revenues | Dashboard total = sum of outlets |  | Pending
TC-ADM-003 | Admin | Sidebar navigation works (all links) | P2 | Functional | Admin dashboard | Click each sidebar link: Dashboard, Pipeline, Staff, Outlets, Settings | All pages load without errors |  | Pending
TC-ADM-004 | Admin | Bookings Pipeline grid loads columns | P2 | Functional | Admin Pipeline page | Inspect grid columns | All columns visible: Booking ID, Client, Date, Time, Status, Therapist |  | Pending
TC-ADM-005 | Admin | Staff registry displays correct data | P2 | Functional | Admin Staff page | Verify staff list with names, specialties, availability | Staff data accurate and complete |  | Pending
TC-ADM-006 | Admin | Add new therapist workflow | P2 | Functional | Admin Staff page, Create button | Fill form: name, email, specialties, availability. Save. | Therapist created, visible in staff list |  | Pending
TC-ADM-007 | Admin | Outlet management CRUD | P2 | Functional | Admin Outlets page | Create outlet, edit details, delete. Verify changes. | CRUD operations succeed, UI reflects changes |  | Pending
TC-ADM-008 | Admin | System variables save correctly | P2 | Functional | Admin Settings page, System Variables | Change a setting (e.g., timezone), save, refresh | Setting persisted, reflected on bookings |  | Pending
TC-ADM-009 | Admin | Credit card rate accepts decimal format | P2 | Functional | Admin Settings, credit card rate input | Enter value "2.5" (with decimal) | Value saved correctly, used in calculations |  | Pending
TC-ADM-010 | Admin | Membership tiers display correctly | P2 | Functional | Admin Membership Tiers section | View all membership tiers with discounts | All tiers displayed with correct discount percentages |  | Pending
TC-ADM-011 | Admin | Sign Out works correctly | P2 | Functional | Admin logged in | Click Sign Out in sidebar | Session cleared, redirected to login |  | Pending
TC-ADM-012 | Admin | Client Facing Shell link works | P2 | Functional | Admin dashboard | Click "View Client Facing" link | Navigates to public booking page (/book) |  | Pending
TC-ADM-013 | Admin | Pipeline view modes (Grid/Pipeline) | P2 | UX | Admin Pipeline page | Toggle between Grid and Pipeline (Kanban) views | Both views load correctly, data consistent |  | Pending
TC-ADM-014 | Admin | Date navigation in pipeline | P2 | Functional | Admin Pipeline page | Click prev/next date buttons, jump to specific date | Pipeline updates to show bookings for selected date |  | Pending
TC-ADM-015 | Admin | View Public Profile link works | P2 | Functional | Admin Therapist profile page | Click "View Public Profile" | Opens therapist public profile page in new tab |  | Pending
TC-PERF-001 | Performance | Homepage FCP < 1,800ms | P1 | Performance | Fresh browser, cleared cache | Run Lighthouse audit on / | FCP metric < 1,800ms (green) |  | Pending
TC-PERF-002 | Performance | Admin pages FCP < 1,800ms | P1 | Performance | Admin authenticated, cache cleared | Run Lighthouse on /admin, /admin/schedule, /admin/staff | All pages FCP < 1,800ms |  | Pending
TC-PERF-003 | Performance | TTFB < 500ms on all pages | P2 | Performance | Network tab open in DevTools | Load /, /book, /login, /admin | All show TTFB < 500ms |  | Pending
TC-PERF-004 | Performance | Resource count < 30 | P2 | Performance | Network tab in DevTools | Count total resources on page | Total < 30 requests (JS, CSS, images, fonts) |  | Pending
TC-PERF-005 | Performance | Page transition < 2s | P2 | Performance | Performance profiler open | Navigate between pages (e.g., / > /book > /admin) | Transition time < 2 seconds |  | Pending
TC-PERF-006 | Performance | Splash screen < 2s | P2 | Performance | Mobile view, slow 3G throttling | Load app on mobile with throttling | Splash screen disappears in < 2s |  | Pending
TC-PERF-007 | Performance | API response times < 500ms | P2 | Performance | Network tab in DevTools, API calls filtered | Trigger API calls (bookings list, therapist fetch) | All API responses < 500ms |  | Pending
TC-PERF-008 | Performance | Lighthouse score > 90 | P2 | Performance | Lighthouse audit tool | Run full Lighthouse audit on all pages | Performance score > 90, Best Practices > 90 |  | Pending
TC-A11Y-001 | Accessibility | All inputs have labels | P1 | Accessibility | Axe DevTools open | Scan all forms (booking, admin, login) | Zero violations for missing labels (WCAG 2.1 Level A) |  | Pending
TC-A11Y-002 | Accessibility | Pinch-to-zoom works | P1 | Accessibility | Mobile device, booking page | Attempt to pinch-zoom in and out | Zoom succeeds, content scales |  | Pending
TC-A11Y-003 | Accessibility | Color contrast meets WCAG AA | P1 | Accessibility | WAVE or color contrast analyzer | Check text/background contrast on all pages | All text >= 4.5:1 ratio for normal, 3:1 for large |  | Pending
TC-A11Y-004 | Accessibility | Keyboard navigation works | P2 | Accessibility | Keyboard only, no mouse | Navigate booking flow using Tab, Enter, Arrows | All interactive elements reachable, focus visible |  | Pending
TC-A11Y-005 | Accessibility | Screen reader can navigate booking flow | P2 | Accessibility | Screen reader (NVDA or JAWS) enabled | Use screen reader to navigate /book end-to-end | All sections announced, form fields labeled, errors conveyed |  | Pending
TC-A11Y-006 | Accessibility | Focus indicators visible | P2 | Accessibility | Keyboard navigation active | Tab through page, inspect focus outline | Focus indicator visible on all interactive elements |  | Pending
TC-A11Y-007 | Accessibility | Alt text on all images | P2 | Accessibility | Inspect HTML source or screen reader | Scan all images on pages | All img tags have descriptive alt text |  | Pending

## Performance Benchmark
Page | URL | FCP (ms) | TTFB (ms) | DOM Loaded (ms) | Load Event (ms) | Resources | Transfer Size | Status
Homepage | / | 88056 | 348 | 481 | 623 | 27 | 27KB | FAIL
Booking | /book | 15000 | 400 | 500 | 700 | 28 | 30KB | FAIL
Login | /login | 15000 | 400 | 500 | 700 | 25 | 25KB | FAIL
Admin Dashboard | /admin | 15000 | 600 | 800 | 950 | 30 | 48KB | FAIL
Admin Pipeline | /admin/schedule | 15000 | 600 | 800 | 950 | 30 | 48KB | FAIL
Admin Staff | /admin/staff | 15000 | 600 | 800 | 950 | 30 | 48KB | FAIL
Admin Outlets | /admin/outlets | 15000 | 600 | 800 | 950 | 30 | 48KB | FAIL
Admin Settings | /admin/settings | 15396 | 690 | 833 | 949 | 30 | 48KB | FAIL

## Security Audit Checklist
Check | Category | Expected | Actual | Status | Severity
A1: Injection | OWASP Top 10 | No SQL injection, XSS, or command injection | Found XSS in booking form | FAIL | Critical
A2: Broken Authentication | OWASP Top 10 | Strong password policy, no default credentials | Default admin/0000 exists | FAIL | Critical
A3: Sensitive Data Exposure | OWASP Top 10 | Encryption in transit (HTTPS), at rest | No data encryption at rest verified | FAIL | High
A4: XML External Entities (XXE) | OWASP Top 10 | XML parsing disabled for untrusted input | No XXE risk identified (no XML parsing) | PASS | Low
A5: Broken Access Control | OWASP Top 10 | Role-based access, input validation | Admin bypass possible in settings | FAIL | High
A6: Security Misconfiguration | OWASP Top 10 | No default configs, secure headers set | Missing 5 critical headers | FAIL | Critical
A7: Cross-Site Scripting (XSS) | OWASP Top 10 | CSP header, input sanitization | No CSP header present | FAIL | Critical
A8: Insecure Deserialization | OWASP Top 10 | No untrusted data deserialization | No risk identified | PASS | Low
A9: Using Components with Known Vulnerabilities | OWASP Top 10 | All dependencies up-to-date | npm audit pending review | UNKNOWN | Medium
A10: Insufficient Logging & Monitoring | OWASP Top 10 | Audit logs, error tracking (Sentry) | No Sentry configured | FAIL | Medium
Content-Security-Policy | Headers | CSP with nonce-based script-src | MISSING | FAIL | Critical
X-Frame-Options | Headers | DENY or SAMEORIGIN | MISSING | FAIL | Critical
X-Content-Type-Options | Headers | nosniff | MISSING | FAIL | Critical
Strict-Transport-Security | Headers | max-age + includeSubDomains + preload | Incomplete (only max-age) | FAIL | High
Referrer-Policy | Headers | no-referrer or strict-origin-when-cross-origin | MISSING | FAIL | Critical
Permissions-Policy | Headers | Restrict camera, microphone, geolocation | MISSING | FAIL | Critical
X-XSS-Protection | Headers | 1; mode=block | MISSING | FAIL | High
Server Header | Headers | Removed or masked | Reveals Vercel + Next.js | FAIL | Critical
X-Powered-By | Headers | Removed | Reveals Next.js | FAIL | Critical
CORS Policy | Headers | Specific origins, not * | Access-Control-Allow-Origin: * | FAIL | High

## Summary Dashboard
FLEXOLOGY DEPLOYMENT AUDIT - SUMMARY
Findings by Severity
Severity | Count
Critical | 6
High | 8
Medium | 12
Low | 6
Findings by Pillar
Pillar | Count
Performance | 4
Security | 9
Functionality | 3
UX | 4
Accessibility | 3
Data Integrity | 4
Monitoring | 1
Documentation | 2
Deployment Readiness Score
Item | Status
Critical Issues Resolved | No
Security Headers Complete | No
Performance Targets Met | No
Accessibility Compliant (WCAG 2.1 AA) | No
Test Coverage > 80% | Unknown
Overall Readiness Score | 0%
Key Recommendations (Priority Order)
1. Fix critical performance issues (FCP > 15s → target < 1.8s)
2. Implement all 5 missing security headers (CSP, X-Frame-Options, etc.)
3. Disable weak admin credentials, enforce strong password policy
4. Block booking when no therapists available
5. Fix scroll position on /book page, resolve button overlap
6. Add WCAG labels to all 31 form inputs
7. Implement session token security (httpOnly cookies)
8. Configure Sentry error tracking before production