## All Findings
ID | Pillar | Severity | Title | Description | Impact | Fix Approach | Effort | Status | v1 Status
FLX-001 | Performance | Critical | FCP 11,660ms — 6.5x above target | Server TTFB acceptable (310-440ms) but client-side rendering blocks for 11+ seconds. Black screen for ~10s before content. | Users abandon before load. Core Web Vitals fail. | SSR/SSG, code-split with next/dynamic, lazy load below-fold, defer non-critical JS | Significant | Open | Open (was 15.4s)
FLX-002 | Security | Critical | 5 security headers missing | CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy all MISSING. Only HSTS present. | Clickjacking, MIME sniffing, XSS, info leakage vulnerabilities | Add all 5 headers in Vercel config or Next.js middleware | Quick Win | Open | Partial (HSTS added)
FLX-003 | Functionality | Critical | /services route returns 404 | "SEE ALL" on homepage leads to dead page showing "Not Found" error | Core navigation broken, users cannot browse services | Create /services page or fix link target | Quick Win | Open | New Finding
FLX-004 | Security | Critical | Trivial admin credentials (0000/admin) | Extremely guessable username and password. No rate limiting. No MFA. | Full admin access compromise | Strong password policy, MFA, rate limiting, account lockout | Moderate | Open | Open
FLX-005 | Security | Critical | Tech stack exposed in headers | Server: Vercel, X-Powered-By: Next.js reveal infrastructure | Targeted CVE attacks possible | poweredByHeader: false, suppress Server header | Quick Win | Open | Open
FLX-006 | Functionality | High | Booking page content above viewport | /book loads with content scrolled above visible area. Users see blank page. | Users confused, may abandon booking | scrollTo(0,0) on mount, CSS fix for initial viewport | Quick Win | Open | Open (not fixed)
FLX-007 | Data Integrity | High | Dashboard revenue shows Rp 0 vs Rp 675K in leaderboard | Gross Settled Revenue card contradicts Outlet Performance Leaderboard totals | Admin cannot trust dashboard data | Debug revenue query — likely status filter mismatch | Moderate | Open | New Finding
FLX-008 | UX | High | Currency format inconsistency (3 formats) | Consumer: "IDR 200K", Admin leaderboard: "Rp 475,000" (comma), Indonesian convention: "Rp 200.000" (period) | Confusing, unprofessional | Shared formatCurrency() utility, standardize to Rp with periods | Moderate | Open | Open (partially)
FLX-009 | Functionality | High | No therapists at Dash Padel outlet | Both staff at Pondok Indah. Dash Padel has zero staff. All bookings fail. | Users always get error for first-listed outlet | Assign staff or hide unstaffed outlets from booking | Quick Win | Open | New Finding
FLX-010 | Data Integrity | High | Staff typo "sports masasge" | indra specialty shows "masasge" instead of "massage" | Unprofessional, may appear on public profiles | Fix typo in DB, add input validation | Quick Win | Open | New Finding
FLX-011 | UX | High | Time format inconsistency (period vs colon) | Forms: 09.00, Cards: 09:00, two formats in same panel | Confusing for admins | Standardize to colon format (09:00) throughout | Quick Win | Open | New Finding
FLX-012 | UX | Medium | Whitespace void below homepage | Empty white area after category tabs, no bottom nav | Looks broken/incomplete | Add footer or constrain height | Quick Win | Open | Open (was fixed, regressed?)
FLX-013 | Data Integrity | Medium | "24 people looking" likely hardcoded | Static urgency indicator, doesn't change | Trust erosion if discovered | Make dynamic or remove | Moderate | Open | New Finding
FLX-014 | Performance | Medium | Logo.png loaded twice | Duplicate network requests for same resource | Wasted bandwidth | Debug component re-render cycle | Quick Win | Open | New Finding
FLX-015 | Data Integrity | Medium | All ratings identical 4.9/5 | Every service shows same rating, no review count | Appears fake | Implement real rating system or remove | Moderate | Open | New Finding
FLX-016 | UX | Medium | Credit card rate decimal format mismatch | Field: 0,02 (comma), Label example: 0.029 (period) | Data entry errors | Standardize format, add validation | Quick Win | Open | New Finding
FLX-017 | Functionality | Medium | Outlet hours vs therapist shift gap | Outlets 08-22, therapists 09-20. Bookable but unfillable slots. | Users select slots that always fail | Align hours or filter by staff availability | Moderate | Open | New Finding
FLX-018 | Functionality | Medium | Pipeline shows "No grid columns" | Schedule grid doesn't display staff columns | Admin can't manage schedule visually | Show staff columns or explain no staff assigned | Quick Win | Open | New Finding
FLX-019 | Data Integrity | Medium | Staff name capitalization inconsistent | "Widi" vs "indra" (lowercase) | Unprofessional appearance | Auto-capitalize on save | Quick Win | Open | New Finding
FLX-020 | Data Integrity | Low | Form pre-filled with test data | "Sarah Jenkins" in Add Therapist form | Appears unfinished | Clear fields, use placeholder attr | Quick Win | Open | New Finding
FLX-021 | Security | Low | No confirmation for system variable changes | Economy Engine saves without confirmation | Accidental changes | Add confirmation modal | Quick Win | Open | New Finding
FLX-022 | UX | Low | No bottom navigation on consumer app | No persistent nav bar for mobile app | Poor navigation UX | Add bottom nav component | Moderate | Open | Open
FLX-023 | UX | Low | "Powered by Jemari App" on 404 | Platform branding exposed on error page | White-label issue | Customize 404 branding | Quick Win | Open | New Finding
FLX-024 | Security | Low | No audit logging for admin actions | No visible trail for staff, outlet, variable changes | No accountability | Implement audit log | Significant | Open | New Finding

## Test Cases
TC-ID | Module | Title | Priority | Type | Preconditions | Steps | Expected Result | Status
TC-HOME-001 | Homepage | Page loads without error | P1 | Positive | User on browser | Navigate to https://flex.jemariapp.com/ | Page loads successfully, no 404 or 500 error
TC-HOME-002 | Homepage | Hero section displays correctly | P1 | Positive | Page loaded | Verify hero image, headline, and CTA buttons visible | All elements display with correct styling
TC-HOME-003 | Homepage | Services category tabs render | P1 | Positive | Page loaded | Scroll to services section, verify category tabs | All category tabs visible and clickable
TC-HOME-004 | Homepage | SEE ALL services link navigates to /services | P2 | Positive | Page loaded, see All link visible | Click SEE ALL link | Navigate to /services page or valid target
TC-HOME-005 | Homepage | Sign Up button navigates correctly | P1 | Positive | Page loaded | Click Sign Up button | Navigate to signup page or modal
TC-HOME-006 | Homepage | Log In button navigates correctly | P1 | Positive | Page loaded | Click Log In button | Navigate to login page or modal
TC-HOME-007 | Homepage | BOOK A SESSION button visible and clickable | P1 | Positive | Page loaded | Verify BOOK A SESSION button visible, click it | Navigate to /book page
TC-HOME-008 | Homepage | Homepage FCP under 1800ms | P1 | Performance | Network throttling: 4G | Load homepage and measure FCP | FCP < 1800ms
TC-BOOK-001 | Booking | Booking page loads (Step 1 - Service Type) | P1 | Positive | Unauthed user | Navigate to /book | Page loads, displays service type selection
TC-BOOK-002 | Booking | Service type selection flow (Step 2) | P2 | Positive | On booking page step 1 | Select a service type, click next | Navigate to step 2 - outlet selection
TC-BOOK-003 | Booking | Outlet selection from list (Step 3) | P2 | Positive | On booking step 2 | Select an outlet with staff, click next | Navigate to step 3 - service selection
TC-BOOK-004 | Booking | Service selection from available services (Step 4) | P2 | Positive | On booking step 3 | Select a service, click next | Navigate to step 4 - date/time selection
TC-BOOK-005 | Booking | Date and time selection (Step 5) | P2 | Positive | On booking step 4 | Select date and time, click next | Navigate to therapist selection or confirmation
TC-BOOK-006 | Booking | Therapist assignment selection | P2 | Positive | On final booking step | Verify therapist list, select therapist | Therapist selected, can proceed to confirmation
TC-BOOK-007 | Booking | Continue booking without therapist selection | P3 | Boundary | On therapist selection step | Try to proceed without selecting therapist | Show warning or prevent progression
TC-BOOK-008 | Booking | Back button navigation in booking flow | P2 | Positive | Any booking step > 1 | Click back button | Return to previous step with data retained
TC-BOOK-009 | Booking | Outlet with no staff shows error | P2 | Negative | Select Dash Padel (no staff) | Try to book at unstaffed outlet | Show error or prevent booking
TC-BOOK-010 | Booking | Booking page content visible (not scrolled above viewport) | P2 | Positive | Navigate to /book | Verify content is visible without scrolling up | Content displays in viewport on page load
TC-BOOK-011 | Booking | Booking flow FCP measurement | P1 | Performance | Network: 4G | Load /book and measure FCP | FCP < 1800ms
TC-BOOK-012 | Booking | Time slot within outlet hours and staff availability | P2 | Boundary | Selecting time slot | Verify available slots align with staff shifts | Only show slots where staff available
TC-ADMIN-001 | Admin Auth | Admin login with valid credentials | P1 | Positive | At /admin login page | Enter valid admin username/password | Redirect to admin dashboard
TC-ADMIN-002 | Admin Auth | Admin login with invalid credentials | P1 | Negative | At /admin login page | Enter invalid username/password | Show error message, stay on login
TC-ADMIN-003 | Admin Auth | Admin login with empty fields | P2 | Boundary | At /admin login page | Leave fields empty, click submit | Show validation error, prevent login
TC-ADMIN-004 | Admin Auth | Admin login rate limiting (brute force) | P2 | Security | At /admin login page | Attempt login 10 times with wrong password | Account locked or request throttled after 5 attempts
TC-DASH-001 | Dashboard | Dashboard metrics display | P1 | Positive | Logged in as admin | Navigate to /admin/dashboard | Revenue, booking count, outlet metrics visible
TC-DASH-002 | Dashboard | Revenue accuracy (Rp 675K in leaderboard) | P2 | Functional | On dashboard | Verify Gross Settled Revenue card total | Total matches Outlet Performance Leaderboard
TC-DASH-003 | Dashboard | Leaderboard displays outlet ranking | P2 | Positive | On dashboard | Scroll to leaderboard section | Outlets ranked by revenue, data accurate
TC-DASH-004 | Dashboard | Dashboard navigation to sub-pages | P2 | Positive | On dashboard | Click links to staff, outlets, bookings | Navigate to respective admin pages
TC-DASH-005 | Dashboard | Currency format consistency (Rp notation) | P2 | Functional | View dashboard metrics | Verify all currency displays use "Rp" with period | All Rp amounts use consistent format
TC-PIPE-001 | Pipeline | Pipeline grid view displays all columns | P1 | Positive | Navigate to /admin/schedule | Verify staff column headers display | All staff columns visible, grid not empty
TC-PIPE-002 | Pipeline | Pipeline view tab accessible | P2 | Positive | On /admin/schedule | Switch to pipeline view if available | View loads with booking status cards
TC-PIPE-003 | Pipeline | Date navigation in pipeline | P2 | Positive | In pipeline view | Use date picker to navigate dates | Pipeline updates to show selected date
TC-PIPE-004 | Pipeline | Pipeline shows no data for outlets with no staff | P2 | Negative | View pipeline for Dash Padel | Scroll through pipeline | Show empty state or message for unstaffed outlet
TC-STAFF-001 | Staff | View all staff members | P1 | Positive | Navigate to /admin/staff | Page loads and displays staff list | All staff members listed with details
TC-STAFF-002 | Staff | Add new therapist | P2 | Positive | On staff page, form clear | Click Add Therapist, fill form, save | New therapist added to list
TC-STAFF-003 | Staff | Edit therapist details | P2 | Positive | Staff list displayed | Click edit on therapist, modify field, save | Changes persisted in staff list
TC-STAFF-004 | Staff | Verify therapist specialty typo correction | P2 | Functional | View Indra staff record | Check specialty field for "massage" vs "masasge" | Specialty correctly spelled as "massage"
TC-STAFF-005 | Staff | Staff working hours/shift consistency | P2 | Functional | View staff shift times | Compare displayed shifts to available booking slots | Shift times align with available time slots
TC-STAFF-006 | Staff | Public staff profile appears on consumer app | P2 | Positive | Consumer side, browse staff profiles | Verify staff names, specialties, capitalization correct | Names properly capitalized, consistent format
TC-OUT-001 | Outlets | View all outlets | P1 | Positive | Navigate to /admin/outlets | Page loads and displays outlet list | All outlets listed (Pondok Indah, Dash Padel)
TC-OUT-002 | Outlets | Add new outlet | P2 | Positive | On outlets page | Click Add Outlet, fill details, save | New outlet added to list
TC-OUT-003 | Outlets | Edit outlet operating hours | P2 | Positive | Click edit on outlet | Modify opening/closing hours, save | Hours updated and reflected in booking availability
TC-OUT-004 | Outlets | Outlet maps/location link functional | P2 | Positive | View outlet details | Click location/maps link | Opens maps or location info correctly
TC-OUT-005 | Outlets | Assign manager/staff to outlet | P2 | Positive | Edit outlet, assign staff field | Assign therapist to Dash Padel outlet | Staff assignment persisted, reflects in bookings
TC-SYS-001 | Settings | View system variables | P1 | Positive | Navigate to /admin/settings | Page loads and displays variables | Economy Engine, membership tiers visible
TC-SYS-002 | Settings | Edit economy engine rate | P2 | Positive | On settings page | Click edit economy rate, change value | New rate applied to system calculations
TC-SYS-003 | Settings | Edit membership tier structure | P2 | Positive | On settings page | Edit membership tiers, save | Changes reflected in user tier assignments
TC-SYS-004 | Settings | Confirmation modal on variable change | P2 | Security | About to save system variable change | Verify confirmation dialog appears before save | Modal prompts for confirmation before saving
TC-PERF-001 | Performance | FCP measurement across pages | P1 | Performance | Network: 4G throttle | Measure FCP on /, /book, /services | All pages FCP < 1800ms (target)
TC-PERF-002 | Performance | TTFB acceptable on all pages | P1 | Performance | Network: 4G | Measure TTFB on key pages | All pages TTFB 300-440ms
TC-PERF-003 | Performance | Resource count optimization | P2 | Performance | DevTools network tab | Count total requests and assets | Homepage < 30 requests, bundle size optimized
TC-PERF-004 | Performance | Mobile page load performance | P2 | Performance | Simulate iPhone 12, 4G network | Load pages and measure metrics | Mobile FCP < 2.5s, usable within 3s
TC-PERF-005 | Performance | No duplicate resource loads | P2 | Performance | Network tab, check resources | Verify logo.png and other assets loaded once | No duplicate network requests
TC-SEC-001 | Security | Security headers present (CSP, X-Frame-Options, etc) | P1 | Security | Navigate to any page | Open DevTools, check Response Headers | All 5 headers present: CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy
TC-SEC-002 | Security | Admin authentication required for /admin routes | P1 | Security | Unauthenticated user | Try to access /admin directly | Redirect to login, prevent unauthorized access
TC-SEC-003 | Security | CORS policy enforced | P2 | Security | Make cross-origin API request | Verify CORS headers restrict requests appropriately | Only same-origin or whitelisted domains allowed
TC-SEC-004 | Security | Tech stack not exposed in headers | P2 | Security | Check response headers | Verify Server header suppressed, no Next.js leak | No "Vercel" or "Next.js" in response headers
TC-SEC-005 | Security | Input validation on forms | P2 | Security | Try to submit forms with special chars/SQL | Verify input sanitization prevents injection | No XSS or injection vulnerabilities
TC-SEC-006 | Security | XSS prevention in user input fields | P2 | Security | Submit <script> tags in input fields | Verify script tags escaped or sanitized | No script execution, tags displayed as text
TC-SEC-007 | Security | CSRF token protection on state-changing requests | P2 | Security | POST/PUT/DELETE requests to API | Verify CSRF tokens present and validated | Requests without valid token rejected

## Performance Benchmark
Page | URL | TTFB (ms) | FCP (ms) | Resources | HTTP Status | Target FCP | Pass/Fail | Notes
/ | https://flex.jemariapp.com/ | 310 | 11660 | 27 | 200 | <1800 | FAIL | 6.5x over target
/book | https://flex.jemariapp.com/book | 340 | 11776 | 25 | 200 | <1800 | FAIL | Content above viewport
/services | https://flex.jemariapp.com/services | 408 | 11212 | 20 | 404 | <1800 | FAIL | Page not found
/admin | https://flex.jemariapp.com/admin | 339 | N/A | N/A | 200 | <1800 | N/A | Server response OK
/admin/schedule | https://flex.jemariapp.com/admin/schedule | 376 | N/A | N/A | 200 | <1800 | N/A | Server response OK
/admin/staff | https://flex.jemariapp.com/admin/staff | 318 | N/A | N/A | 200 | <1800 | N/A | Server response OK
/admin/outlets | https://flex.jemariapp.com/admin/outlets | 407 | N/A | N/A | 200 | <1800 | N/A | Server response OK
/admin/settings | https://flex.jemariapp.com/admin/settings | 309 | N/A | N/A | 200 | <1800 | N/A | Server response OK

## Security Checklist
Check Item | Category | Status | Current Value | Required Value | Notes
HSTS | Headers | PASS | max-age=63072000 | max-age=31536000 | Fixed from v1
CSP | Headers | FAIL | MISSING | script-src 'self' | No XSS protection
X-Frame-Options | Headers | FAIL | MISSING | DENY | Clickjacking vulnerability
X-Content-Type-Options | Headers | FAIL | MISSING | nosniff | MIME sniffing risk
Referrer-Policy | Headers | FAIL | MISSING | strict-origin-when-cross-origin | Info leakage
Permissions-Policy | Headers | FAIL | MISSING | camera=(), microphone=() | Unnecessary API access
Server Header | Headers | FAIL | Vercel | Not exposed | Tech stack revealed
X-Powered-By | Headers | FAIL | Next.js | Not exposed | Framework revealed
CORS | Access Control | PASS | Not set (same-origin) | Restricted origins | Improved from v1
Admin Auth | Authentication | FAIL | 0000/admin | Strong credentials | Trivially guessable
Rate Limiting | Authentication | FAIL | Not observed | After 5 attempts | No brute force protection
MFA | Authentication | FAIL | Not implemented | Required for admin | No second factor
HTTPS | Transport | PASS | TLS active | TLS required | Properly configured
localStorage Sensitive Data | Data Storage | PASS | No sensitive data | No sensitive data | Fixed from v1
Debug Endpoints | Exposure | PASS | All 404 | All 404 | No exposed endpoints
Input Validation | Injection | N/A | Not tested | Server-side validation | Requires code access
Session Management | Auth | PASS | Redirect on no auth | Redirect/403 | Admin redirects to home
Audit Logging | Monitoring | FAIL | Not visible | All admin actions logged | No accountability

## Summary Dashboard
Flexology v2 Deployment Audit - Summary Dashboard
Findings by Severity |  | Findings by Pillar
Critical | 5 | Performance | 2
High | 6 | Security | 5
Medium | 8 | Functionality | 5
Low | 5 | UX | 5
Total | 24 | Data Integrity | 7
Findings by Status |  | v1 Comparison
Open | 24 | v1 Fixed | 8
Fixed | 0 | v1 Still Open | 11
Total | 24 | New in v2 | 13
|  | Regressed | 1
Security Headers Summary |  | Deployment Readiness Score
Pass | 1 | Overall Score | 5.4
Fail | 7 | Scale: 0-10