## All Findings
Finding ID | Category | Title | Severity | Priority | V5 Status | V6 Status | Description | Impact | Recommended Fix | Effort Estimate | Sprint Assignment
V6-001 | Functionality | POS Module Accessibility | Critical | P1 | Claimed Fixed | Needs Verification | POS module was claimed fixed but could not be conclusively verified due to session issues | Entire POS business module potentially inaccessible | Verify POS routing, test /pos endpoint independently | 2h verification | Sprint 1
V6-002 | Data Integrity | Revenue Data Mismatch | Critical | P1 | Claimed Fixed | STILL BROKEN | Executive Dashboard shows Rp 0 in Gross Settled Revenue but Outlet Leaderboard shows Rp 875,000 | Financial reporting is wrong — business decisions based on incorrect data | Fix totalRevenue aggregation hook, ensure KPI card pulls from same data source as leaderboard | 4-8h | Sprint 1
V6-003 | UI/UX | Pre-filled Sample Data in Forms | High | P1 | Claimed Fixed | STILL PRESENT | Registration and booking forms still contain placeholder/sample data | Unprofessional appearance, confuses real users, pollutes database | Remove all hardcoded test data from form defaults, use empty strings | 2-4h | Sprint 2
V6-004 | UI/UX | Password Visibility Toggle Missing | Medium | P3 | Claimed Fixed | NOT IMPLEMENTED | Registration modal lacks Eye/EyeOff password toggle controls | Users cannot verify password input, increases registration friction | Add password toggle component to registration form using Eye/EyeOff icons from lucide-react | 2-3h | Sprint 3
V6-005 | Performance | Homepage FCP Critical Regression | Critical | P1 | Was 400-628ms | REGRESSED to 21.8s | Homepage First Contentful Paint measured at 21.8 seconds — 35x slower than V5 | Homepage is unusable, users will abandon before content loads | Investigate bundle size, check for blocking resources, verify dynamic imports working, check Vercel build output | 4-8h | Sprint 1
V6-006 | Functionality | Booking Flow Navigation Broken | Critical | P1 | Not Previously Found | NEW ISSUE | Continue button in booking flow does not advance to next step | Primary business flow is completely non-functional, zero conversions possible | Debug booking flow state machine, check onClick handlers, verify routing between booking steps | 4-8h | Sprint 1
V6-007 | Functionality | Services Page Requires Auth | Medium | P3 | Not Previously Found | NEW ISSUE | /services page redirects to login instead of being publicly accessible | Reduces service discoverability, users must register before browsing | Update middleware.ts to exclude /services from auth-protected routes | 1-2h | Sprint 3
V6-008 | UI/UX | Admin Session Timeout Too Short | Medium | P2 | Not Previously Found | NEW ISSUE | Admin session expires rapidly during normal page navigation | Admins cannot complete workflows, forced to re-login repeatedly | Increase JWT expiry, implement token refresh mechanism | 4-6h | Sprint 3
V6-009 | Security | Security Headers Missing | High | P2 | Partially Fixed | STILL INCOMPLETE | CSP and X-Frame-Options absent, X-Powered-By exposed. HSTS present. | Clickjacking risk, content injection risk, server fingerprinting | Add CSP, X-Frame-Options: DENY, remove X-Powered-By in next.config.js headers | 2-4h | Sprint 2
V6-010 | Security | Default Admin Credentials Active | Critical | P1 | Not Changed | STILL ACTIVE | Admin login accepts 0000/admin with no forced password change | Anyone can access admin panel with known default credentials | Force password change on first login, implement password complexity requirements | 4-6h | Sprint 1
V6-011 | Security | Admin Auth Route Inconsistency | High | P2 | Was Fixed in V5 | INCONSISTENT | V5 confirmed auth redirect working, V6 found /admin sometimes accessible without auth | Potential unauthorized access to admin panel | Review middleware.ts auth logic, check for caching issues, test with cleared cookies | 4-6h | Sprint 2
V6-012 | Security | XSS in Registration Form | High | P2 | Not Previously Found | NEW ISSUE | XSS payload in name field not sanitized | Cross-site scripting vulnerability, session hijacking risk | Implement input sanitization on all form fields, use DOMPurify or similar library | 3-4h | Sprint 2

## Quick Wins
Finding ID | Category | Title | Severity | Priority | V5 Status | V6 Status | Description | Impact | Recommended Fix | Effort Estimate | Sprint Assignment
V6-001 | Functionality | POS Module Accessibility | Critical | P1 | Claimed Fixed | Needs Verification | POS module was claimed fixed but could not be conclusively verified due to session issues | Entire POS business module potentially inaccessible | Verify POS routing, test /pos endpoint independently | 2h verification | Sprint 1
V6-003 | UI/UX | Pre-filled Sample Data in Forms | High | P1 | Claimed Fixed | STILL PRESENT | Registration and booking forms still contain placeholder/sample data | Unprofessional appearance, confuses real users, pollutes database | Remove all hardcoded test data from form defaults, use empty strings | 2-4h | Sprint 2
V6-007 | Functionality | Services Page Requires Auth | Medium | P3 | Not Previously Found | NEW ISSUE | /services page redirects to login instead of being publicly accessible | Reduces service discoverability, users must register before browsing | Update middleware.ts to exclude /services from auth-protected routes | 1-2h | Sprint 3
V6-009 | Security | Security Headers Missing | High | P2 | Partially Fixed | STILL INCOMPLETE | CSP and X-Frame-Options absent, X-Powered-By exposed. HSTS present. | Clickjacking risk, content injection risk, server fingerprinting | Add CSP, X-Frame-Options: DENY, remove X-Powered-By in next.config.js headers | 2-4h | Sprint 2

## Improvement Roadmap
Flexology V6 - 4-Week Improvement Roadmap
Sprint 1 (Week 1) | (BLOCKERS)
V6-001 - POS Module Accessibility (2h verification)
V6-002 - Revenue Data Mismatch (4-8h)
V6-005 - Homepage FCP Critical Regression (4-8h)
V6-006 - Booking Flow Navigation Broken (4-8h)
V6-010 - Default Admin Credentials Active (4-6h)
Sprint 2 (Week 2) | (HIGH PRIORITY)
V6-003 - Pre-filled Sample Data in Forms (2-4h)
V6-009 - Security Headers Missing (2-4h)
V6-011 - Admin Auth Route Inconsistency (4-6h)
V6-012 - XSS in Registration Form (3-4h)
Sprint 3 (Week 3) | (MEDIUM PRIORITY)
V6-004 - Password Visibility Toggle Missing (2-3h)
V6-007 - Services Page Requires Auth (1-2h)
V6-008 - Admin Session Timeout Too Short (4-6h)
Sprint 4 (Week 4) | (STABILIZATION)
Hardening & code review
Monitoring & alerting setup
Regression testing
Performance optimization

## Summary Dashboard
Flexology V6 QA Audit Summary
OVERALL METRICS
Total Findings | 12
Critical Issues | 5
High Priority | 4
Medium Priority | 3
V5 CLAIM VERIFICATION
Claims Verified | 0
Claims Broken | 4
New Issues Found | 4
DEPLOYMENT SCORE
V6 Score | 3.2/10
Status | REGRESSED from 5.8/10