## Security Findings
ID | Category | Title | Severity | OWASP Category | V5 Status | V6 Status | Description | Proof of Concept | Remediation | Effort | Sprint
SEC-001 | Access Control | POS Module 404 / Inaccessible | Critical | A01:2021 Broken Access Control | Claimed Fixed | Needs Verification | POS module accessibility could not be conclusively verified due to session timeout issues during V6 audit | Navigate to /pos — verify it renders POS interface | Verify POS route in middleware.ts, add POS link to sidebar | 2-4h | Sprint 1
SEC-002 | Authentication | Admin Auth Redirect | Medium | A07:2021 Auth Failures | Verified Fixed in V5 | INCONSISTENT | V5 confirmed unauthenticated /admin access redirects to login. V6 found /admin sometimes accessible without auth — possible caching or cookie state | 1. Clear all cookies 2. Navigate to /admin 3. Should redirect to /login | Review middleware.ts JWT verification, check edge caching, test in incognito | 4-6h | Sprint 2
SEC-003 | Security Config | Missing Security Headers | High | A05:2021 Security Misconfiguration | Partially Fixed | STILL INCOMPLETE | CSP header absent, X-Frame-Options absent, X-Powered-By exposed. Only HSTS present. | curl -I https://flex.jemariapp.com — check response headers | Add to next.config.js: CSP policy, X-Frame-Options: DENY, remove X-Powered-By via poweredByHeader: false | 2-4h | Sprint 2
SEC-004 | Authentication | Default Admin Credentials | Critical | A07:2021 Auth Failures | Not Changed | STILL ACTIVE | Admin panel accessible with default credentials 0000/admin. No forced password change mechanism. | 1. Go to /admin/login 2. Enter username: 0000 3. Enter password: admin 4. Access granted | Implement first-login password change, add complexity requirements (min 8 chars, upper/lower/number/special) | 4-6h | Sprint 1
SEC-005 | Authentication | No Login Rate Limiting | High | A07:2021 Auth Failures | Needs Testing | NOT TESTED | No evidence of rate limiting on login endpoint. Brute force attacks possible. | Attempt 20+ rapid login requests with wrong credentials — check if any throttling occurs | Implement rate limiting: max 5 attempts per IP per 5 minutes, progressive lockout | 4-6h | Sprint 2
SEC-006 | Input Validation | XSS in Registration Form | High | A03:2021 Injection | Not Found in V5 | NEW FINDING | Name field in registration form does not sanitize script input | Enter <script>alert('xss')</script> in name field during registration | Implement server-side input sanitization, use DOMPurify on client, validate all inputs | 3-4h | Sprint 2
SEC-007 | Data Exposure | Pre-filled Form Data | Medium | A01:2021 Broken Access Control | Claimed Fixed | STILL PRESENT | Forms contain pre-filled sample/test data visible to all users | Navigate to registration form — observe pre-filled values | Remove all hardcoded test data from form default values | 2h | Sprint 2
SEC-008 | Session Mgmt | Short Admin Session Timeout | Medium | A07:2021 Auth Failures | Not Found in V5 | NEW FINDING | Admin sessions expire too quickly during normal navigation between pages | Login to admin, navigate through 3-4 pages, observe forced re-login | Increase JWT token expiry, implement silent token refresh on API calls | 4-6h | Sprint 3
SEC-009 | Session Mgmt | Session Cookie Flags | High | A07:2021 Auth Failures | Needs Testing | NOT TESTED | flex_session cookie security flags (HttpOnly, Secure, SameSite) not verified | Check cookie in browser DevTools: Application > Cookies | Set cookie flags: HttpOnly=true, Secure=true, SameSite=Strict | 1-2h | Sprint 2
SEC-010 | Security Config | Server Information Exposure | Medium | A05:2021 Security Misconfiguration | Claimed Fixed | PARTIALLY FIXED | X-Powered-By header still reveals server technology. Server header status unclear. | curl -I https://flex.jemariapp.com ¦ grep -i "x-powered" | Set poweredByHeader: false in next.config.js, verify on deployment | 30min | Sprint 2
SEC-011 | Access Control | Services Page Auth Requirement | Medium | A01:2021 Broken Access Control | Not Found in V5 | NEW FINDING | /services requires authentication but should be publicly accessible for service browsing | Navigate to /services without login — observe redirect to login | Update middleware.ts matcher to exclude /services from protected routes | 1-2h | Sprint 3
SEC-012 | Data Integrity | Revenue Data Discrepancy | Critical | A04:2021 Insecure Design | Claimed Fixed | STILL BROKEN | Dashboard KPI shows Rp 0 while leaderboard shows Rp 875,000 — potential data manipulation or aggregation flaw | Compare Executive Dashboard KPI card value with sum of Outlet Leaderboard values | Audit data aggregation pipeline, ensure single source of truth for revenue calculations | 4-8h | Sprint 1

## OWASP Top 10 Checklist
Category | Name | Status | Findings | Risk Level | Notes
A01:2021 | Broken Access Control | PARTIAL FAIL | SEC-001, SEC-007, SEC-011 | High | POS access uncertain, auth routes inconsistent
A02:2021 | Cryptographic Failures | NEEDS TESTING | None found | Medium | TLS present but cookie encryption not verified
A03:2021 | Injection | FAIL | SEC-006 | High | XSS confirmed in registration
A04:2021 | Insecure Design | FAIL | SEC-012 | Critical | Revenue data integrity compromise
A05:2021 | Security Misconfiguration | PARTIAL FAIL | SEC-003, SEC-010 | High | Missing headers, server info exposed
A06:2021 | Vulnerable Components | NEEDS TESTING | None found | Medium | Dependency audit not performed
A07:2021 | Auth Failures | FAIL | SEC-002, SEC-004, SEC-005, SEC-008, SEC-009 | Critical | Default creds, no rate limiting, session issues
A08:2021 | Software & Data Integrity | NEEDS TESTING | None found | Medium | CI/CD pipeline integrity not verified
A09:2021 | Logging & Monitoring | NEEDS TESTING | None found | Medium | No evidence of security logging
A10:2021 | SSRF | NEEDS TESTING | None found | Low | No SSRF vectors identified

## Remediation Roadmap
Phase | Timeline | Finding IDs | Actions | Success Criteria
BLOCKER (Pre-Deploy) | Week 1 | SEC-001, SEC-004, SEC-012 | Verify POS access, force password change, fix revenue aggregation | POS accessible, no default creds, revenue data matches
HIGH (Week 1-2) | Week 2 | SEC-003, SEC-005, SEC-006, SEC-009 | Add security headers, implement rate limiting, fix XSS, verify cookie flags | All headers present, rate limiting active, no XSS, secure cookies
MEDIUM (Week 2-3) | Week 3 | SEC-002, SEC-007, SEC-008, SEC-010, SEC-011 | Fix auth inconsistency, remove sample data, extend sessions, remove server info, fix /services | Consistent auth, clean forms, stable sessions, no info leakage
HARDENING (Week 3-4) | Week 4 | All | Dependency audit, penetration test, security logging, incident response plan | Full OWASP compliance, monitoring active

## Summary
Flexology V6 Security Assessment Summary
Total Security Findings: | 12
Critical: | 3
High: | 4
Medium: | 5
OWASP Categories Failing: | 4
OWASP Categories Needing Testing: | 4
OWASP Categories Passing: | 1
V5 Claims Verified: | 0
V5 Claims Still Broken: | 4
New Findings in V6: | 4
Deployment Blocker Count: | 3
Security Readiness: | NOT READY