## All Findings
ID | Area | Category | Title | Description | Severity | v2 Status | Impact | Effort | Priority | Status | Recommendation
V3-001 | All | Performance | FCP 13-15s across all pages (7x above target) | Critical rendering path issue affecting all pages with FCP of 13-15 seconds | Critical | Open (worse) | Critical | Significant | P1 |  | Profile critical rendering path, defer render-blocking JS, implement SSR/SSG, code-split with next/dynamic. Target FCP < 1,800ms.
V3-002 | Consumer | Performance | Homepage TTFB regression 4,339ms (was 309ms) | Homepage time-to-first-byte increased 14x from 309ms to 4,339ms | Critical | New | Critical | Moderate | P1 |  | Investigate homepage serverless function cold starts, add edge caching, check if homepage data fetching is causing delay.
V3-003 | POS | Functional | POS system does not exist (/pos returns 404) | POS endpoint returns 404, system not deployed | Critical | New | Critical | Major | P1 |  | Build and deploy POS module, or remove from launch scope.
V3-004 | All | Security | Five security headers missing (CSP, X-Frame, etc.) | CSP, X-Frame-Options, X-Content-Type-Options, HSTS headers not configured | Critical | Open | Critical | Quick Win | P1 |  | Add security headers via Next.js middleware or vercel.json headers config.
V3-005 | All | Security | Tech stack exposed via Server/X-Powered-By headers | Server and X-Powered-By headers reveal tech stack information | Critical | Open | High | Quick Win | P1 |  | Configure Vercel to suppress Server header, remove X-Powered-By in next.config.js with poweredByHeader: false.
V3-006 | Admin | Security | Admin credentials trivially guessable (0000/admin) | Default credentials easily guessable, no rate limiting observed | Critical | Open | Critical | Moderate | P1 |  | Change to strong credentials, implement rate limiting, add MFA for admin.
V3-007 | Consumer | Functional | SEE ALL link on homepage non-functional | Link on homepage does not navigate or respond to clicks | High | New | High | Quick Win | P2 |  | Add proper href or onClick handler to "SEE ALL" link targeting /services page.
V3-008 | Admin | Functional | Admin sidebar navigation broken (click does nothing) | Sidebar links in admin do not navigate | High | New | High | Moderate | P2 |  | Debug client-side router on admin sidebar — likely Next.js Link component issue or event handler conflict.
V3-009 | Admin | UX | Naming mismatches across 3 admin pages | Sidebar labels don't match page titles | High | New | Medium | Quick Win | P2 |  | Align sidebar labels with page titles across all admin pages.
V3-010 | Admin | Functional | Operations Pipeline "No grid columns available" | Grid in Operations Pipeline shows no staff columns | High | New | High | Moderate | P2 |  | Configure grid columns to show assigned staff/therapists.
V3-011 | Admin | Data | Revenue mismatch (Rp 0 vs Rp 875K in leaderboard) | Dashboard shows different revenue totals than leaderboard | High | Open | High | Moderate | P2 |  | Debug revenue aggregation query — ensure settled bookings are included in gross revenue calculation.
V3-012 | All | UX | Currency format inconsistency (3 different formats) | Currency displays in 3 different formats across application | High | Open | Medium | Moderate | P2 |  | Standardize all currency to "Rp XXX.XXX" format with period separators (Indonesian standard).
V3-013 | Consumer | Functional | /services has no dedicated page (redirects to home) | Services page missing, redirect loops to homepage | High | Partial fix | Medium | Moderate | P2 |  | Create dedicated /services page with full service catalog listing.
V3-014 | Admin | Data | Therapist name "indra" not capitalized | Staff name appears as lowercase in registry | Medium | New | Low | Quick Win | P3 |  | Capitalize "indra" to "Indra" in database.
V3-015 | Admin | UX | Staff form pre-filled with "Sarah Jenkins" data | New staff form contains placeholder data on load | Medium | New | Low | Quick Win | P3 |  | Clear placeholder values in new staff form on component mount.
V3-016 | Consumer | UX | Contact details hidden behind Confirm Booking button | Contact information not visible until after confirmation | Medium | New | Medium | Quick Win | P3 |  | Move Confirm Booking button below Contact Details, or make page scrollable.
V3-017 | Admin | UX | Time format inconsistency (periods vs colons) | Time displays with periods and colons across admin pages | Medium | New | Low | Quick Win | P3 |  | Standardize time format to colons (09:00) across all admin pages.
V3-018 | Admin | Data | Credit card rate uses comma decimal (0,02) | Payment rate format uses comma instead of period | Medium | New | Low | Quick Win | P3 |  | Use period decimal (0.02) consistent with international standard.
V3-019 | Consumer | Functional | Service-therapist mismatch in booking flow | Selected service doesn't match available therapist specialties | Medium | New | Medium | Moderate | P3 |  | Filter therapist list by selected service specialty in booking flow.
V3-020 | Admin | Data | Pondok Indah missing from dashboard leaderboard | Outlet not shown in performance leaderboard | Medium | New | Medium | Quick Win | P3 |  | Include all outlets (including Pondok Indah) in leaderboard query.
V3-021 | Admin | Data | Staff assignment inconsistency (location vs dispatch) | Staff outlet assignment conflicts with dispatch assignment | Medium | New | Medium | Moderate | P3 |  | Reconcile staff assigned outlet vs dispatch status.
V3-022 | Consumer | UX | "24 people looking" possibly hardcoded scarcity | Scarcity indicator may not reflect real-time data | Low | New | Low | Quick Win | P4 |  | Make scarcity indicator dynamic based on real-time data, or remove.
V3-023 | All | UX | No responsive desktop layout (mobile-only) | Application only responsive to mobile sizes | Low | Open | Low | Significant | P4 |  | Add responsive desktop layout with max-width container for desktop viewports.
V3-024 | Consumer | UX | Login field "MOBILE NUMBER" accepts admin code | Login field label suggests mobile but accepts admin credentials | Low | New | Low | Quick Win | P4 |  | Create separate admin login flow or relabel field to "ID / Mobile Number".
V3-025 | All | UX | Custom 404 page text generic/unprofessional | 404 error page lacks branding and helpful navigation | Low | New | Low | Quick Win | P4 |  | Customize 404 page with Flexology branding and helpful navigation.

## Test Cases
TC-ID | Module | Title | Priority | Type | Preconditions | Test Data | Steps | Expected Result | Status
TC-USER-001 | Consumer | Homepage loads within 2.5s FCP | P1 | Performance | Clean browser cache | N/A | 1. Navigate to homepage 2. Measure FCP using DevTools | FCP < 2,500ms
TC-USER-002 | Consumer | Homepage TTFB under 800ms | P1 | Performance | Network monitoring enabled | N/A | 1. Navigate to homepage 2. Measure TTFB in DevTools | TTFB < 800ms
TC-USER-003 | Consumer | BOOK A SESSION button navigates to /book | P1 | Positive | Homepage loaded | N/A | 1. Click BOOK A SESSION button | Navigate to /book page
TC-USER-004 | Consumer | SEE ALL link navigates to services listing | P1 | Positive | Homepage loaded | N/A | 1. Click SEE ALL link | Navigate to /services page with service list
TC-USER-005 | Consumer | Featured Services display with correct pricing | P1 | Positive | Homepage loaded | N/A | 1. View featured services on homepage | Services display with pricing in Rp format
TC-USER-006 | Consumer | Login with valid mobile number and password | P1 | Positive | Login page loaded | Mobile: +628123456789, Password: ValidPass123 | 1. Enter mobile and password 2. Click Login | Redirect to booking page, user logged in
TC-USER-007 | Consumer | Login with invalid credentials shows error | P1 | Negative | Login page loaded | Mobile: +629999999999, Password: WrongPass | 1. Enter mobile and password 2. Click Login | Display error message, remain on login page
TC-USER-008 | Consumer | Booking flow Step 1 — Select In Studio shows outlets | P1 | Positive | Booking page loaded | N/A | 1. Click In Studio option 2. View outlet selection | Show Dash Padel and Pondok Indah outlets
TC-USER-009 | Consumer | Booking flow Step 1 — Select At-Home Service | P2 | Positive | Booking page loaded | N/A | 1. Click At-Home Service option | Service options load without outlet selection
TC-USER-010 | Consumer | Booking flow — Select Dash Padel outlet shows services | P1 | Positive | Outlet selection page loaded | N/A | 1. Select Dash Padel outlet | Display services available at Dash Padel
TC-USER-011 | Consumer | Booking flow — Select Pondok Indah outlet shows services | P1 | Positive | Outlet selection page loaded | N/A | 1. Select Pondok Indah outlet | Display services available at Pondok Indah
TC-USER-012 | Consumer | Booking flow — Service selection shows price and duration | P1 | Positive | Service selection page loaded | N/A | 1. Select a service | Show price in Rp format and duration in minutes
TC-USER-013 | Consumer | Booking flow — Time slot selection shows available slots | P1 | Positive | Service selected | N/A | 1. View time slot selection | Show available time slots for selected date
TC-USER-014 | Consumer | Booking flow — Therapist selection shows available therapists | P1 | Positive | Time slot selected | N/A | 1. View therapist selection | Show available therapists with specialties matching service
TC-USER-015 | Consumer | Booking flow — Summary shows correct service, time, outlet, price | P1 | Positive | Therapist selected | N/A | 1. View booking summary | Summary displays all selected details accurately
TC-USER-016 | Consumer | Booking flow — Contact details visible before confirmation | P2 | Positive | Booking summary page loaded | N/A | 1. Scroll to view contact details 2. Verify visibility | Contact details visible without clicking Confirm
TC-USER-017 | Consumer | Currency format uses Rp with period separators throughout | P2 | Positive | Multiple pages visited | N/A | 1. Navigate through booking flow 2. Check all prices | All prices use Rp XXX.XXX format
TC-USER-018 | Consumer | /services page loads with full service catalog | P2 | Positive | N/A | N/A | 1. Navigate to /services | Page loads with complete service list and descriptions
TC-USER-019 | Consumer | 24 people looking indicator reflects real data | P3 | Positive | Homepage loaded, bookings active | N/A | 1. Check scarcity indicator 2. Verify against backend count | Indicator shows real-time or accurate data
TC-USER-020 | Consumer | App renders properly on desktop viewport | P3 | Positive | Desktop viewport (1920x1080) | N/A | 1. Open app on desktop 2. Verify layout | App displays correctly without mobile-only styling
TC-ADMIN-001 | Admin | Admin login with 0000/admin redirects to /admin | P1 | Positive | Admin login page loaded | Username: 0000, Password: admin | 1. Enter credentials 2. Click Login | Redirect to /admin dashboard
TC-ADMIN-002 | Admin | Unauthenticated /admin access redirects to homepage | P1 | Security | Not logged in | N/A | 1. Navigate directly to /admin | Redirect to homepage
TC-ADMIN-003 | Admin | Dashboard Gross Settled Revenue matches leaderboard total | P1 | Positive | Admin dashboard loaded | N/A | 1. Note Gross Revenue on dashboard 2. Check leaderboard total 3. Compare | Both values match exactly
TC-ADMIN-004 | Admin | Dashboard Total Lifetime Bookings count is accurate | P1 | Positive | Admin dashboard loaded | N/A | 1. Note Total Bookings 2. Verify against database | Count matches actual bookings
TC-ADMIN-005 | Admin | Dashboard Confirmed Sessions count is accurate | P1 | Positive | Admin dashboard loaded | N/A | 1. Note Confirmed Sessions 2. Query confirmed status bookings | Count matches confirmed bookings
TC-ADMIN-006 | Admin | Outlet Performance Leaderboard shows ALL outlets | P2 | Positive | Leaderboard page loaded | N/A | 1. View leaderboard table | All outlets (Dash Padel, Pondok Indah) visible
TC-ADMIN-007 | Admin | Sidebar Bookings Pipeline click navigates to schedule | P1 | Positive | Admin dashboard loaded | N/A | 1. Click Bookings Pipeline in sidebar | Navigate to Operations Pipeline page
TC-ADMIN-008 | Admin | Sidebar Staff Registry click navigates to staff | P1 | Positive | Admin dashboard loaded | N/A | 1. Click Staff Registry in sidebar | Navigate to staff management page
TC-ADMIN-009 | Admin | Sidebar Outlets & Managers click navigates to outlets | P1 | Positive | Admin dashboard loaded | N/A | 1. Click Outlets & Managers in sidebar | Navigate to outlets page
TC-ADMIN-010 | Admin | Sidebar System Variables click navigates to settings | P1 | Positive | Admin dashboard loaded | N/A | 1. Click System Variables in sidebar | Navigate to settings/variables page
TC-ADMIN-011 | Admin | Page titles match sidebar labels | P2 | Positive | All admin pages visited | N/A | 1. Visit each admin section 2. Compare title with sidebar label | All titles match labels exactly
TC-ADMIN-012 | Admin | Operations Pipeline shows staff columns in grid | P1 | Positive | Operations Pipeline page loaded | N/A | 1. View pipeline grid | Grid displays staff/therapist columns with data
TC-ADMIN-013 | Admin | Operations Pipeline displays bookings correctly | P1 | Positive | Operations Pipeline page loaded | N/A | 1. View pipeline bookings | All confirmed and pending bookings display
TC-ADMIN-014 | Admin | Staff Registry — Add new therapist with valid data | P1 | Positive | Staff Registry page loaded, form empty | Name: John Doe, Phone: 081234567890, Specialty: Massage | 1. Fill form with valid data 2. Click Save | Therapist added and appears in registry
TC-ADMIN-015 | Admin | Staff Registry — Form empty on load (no placeholder data) | P2 | Positive | Staff Registry page loaded | N/A | 1. Open add staff form | Form fields are empty, no placeholder values
TC-ADMIN-016 | Admin | Staff Registry — Therapist names properly capitalized | P2 | Positive | Staff Registry page loaded | N/A | 1. View staff list | All names properly capitalized (e.g., Indra not indra)
TC-ADMIN-017 | Admin | Outlets — Both outlets show as Active | P1 | Positive | Outlets page loaded | N/A | 1. View outlets list | Dash Padel and Pondok Indah both marked Active
TC-ADMIN-018 | Admin | Outlets — VIEW ON MAPS links open Google Maps | P2 | Positive | Outlets page loaded | N/A | 1. Click VIEW ON MAPS link | Open Google Maps with outlet location
TC-ADMIN-019 | Admin | Outlets — Add new outlet with valid data | P2 | Positive | Outlets page loaded | Name: New Outlet, Address: Jakarta, Phone: 081234567890 | 1. Fill outlet form 2. Click Save | Outlet added to list
TC-ADMIN-020 | Admin | System Variables — Save Registration Bonus updates value | P2 | Positive | System Variables page loaded | New value: Rp 100.000 | 1. Change Registration Bonus value 2. Click Save | Value updated and persisted
TC-ADMIN-021 | Admin | System Variables — Payment fees display correctly | P2 | Positive | System Variables page loaded | N/A | 1. View payment fees section | All fees display with proper Rp format
TC-ADMIN-022 | Admin | System Variables — Credit card rate uses proper decimal | P3 | Positive | System Variables page loaded | N/A | 1. View credit card fee 2. Check decimal format | Rate shows 0.02 not 0,02
TC-ADMIN-023 | Admin | Admin FCP under 2,500ms | P1 | Performance | Admin dashboard loaded, cache cleared | N/A | 1. Measure FCP in DevTools | FCP < 2,500ms
TC-ADMIN-024 | Admin | Currency format consistent across all admin pages | P2 | Positive | All admin pages visited | N/A | 1. Navigate through admin 2. Check all currency values | All use Rp XXX.XXX format
TC-ADMIN-025 | Admin | Time format consistent across all admin pages (colons) | P2 | Positive | All admin pages visited | N/A | 1. Navigate through admin 2. Check all time values | All use HH:MM format (e.g., 09:00)
TC-ADMIN-026 | Admin | Admin auth — rate limiting after failed login attempts | P2 | Security | Admin login page | Invalid credentials | 1. Enter invalid creds 5+ times 2. Attempt login again | Account locked or rate limited
TC-ADMIN-027 | Admin | Admin auth — strong password enforcement | P2 | Security | Admin user creation context | Password: weak123 | 1. Attempt to set weak password | Reject password, show strength requirements
TC-ADMIN-028 | Admin | Sign Out button logs out and redirects | P1 | Positive | Admin logged in | N/A | 1. Click Sign Out button | Clear session, redirect to homepage
TC-ADMIN-029 | Admin | Client Facing Shell link navigates to homepage | P3 | Positive | Admin dashboard loaded | N/A | 1. Click Client Facing Shell link | Navigate to homepage
TC-ADMIN-030 | Admin | Admin pages load without console errors | P2 | Positive | Admin pages loaded | N/A | 1. Open DevTools Console 2. Navigate admin pages | No errors in console
TC-POS-001 | POS | POS system accessible at /pos or dedicated route | P1 | Positive | N/A | N/A | 1. Navigate to /pos | POS page loads successfully
TC-POS-002 | POS | POS requires authentication before access | P1 | Security | Not logged in | N/A | 1. Attempt to access /pos without auth 2. Try valid auth | Redirect to login when unauthenticated; allow access when authenticated
TC-POS-003 | POS | POS shows current day bookings | P1 | Positive | POS authenticated, bookings exist | N/A | 1. Open POS dashboard 2. View bookings list | Display all bookings for current date
TC-POS-004 | POS | POS allows check-in of confirmed bookings | P1 | Positive | POS authenticated, confirmed booking exists | Booking ID: BK-12345 | 1. Select confirmed booking 2. Click Check-in | Booking marked as checked in
TC-POS-005 | POS | POS processes payment for walk-in customers | P1 | Positive | POS authenticated | Service: Massage, Amount: Rp 500.000 | 1. Register walk-in customer 2. Process payment | Payment recorded, receipt generated
TC-POS-006 | POS | POS generates receipt after payment | P2 | Positive | Payment processed | N/A | 1. Complete payment 2. View receipt | Receipt displays transaction details
TC-POS-007 | POS | POS handles refund/void transactions | P2 | Negative | Transaction recorded | Transaction ID: TXN-98765 | 1. Select transaction 2. Click Refund/Void 3. Confirm | Transaction voided, amount credited
TC-POS-008 | POS | POS displays correct pricing in Rp format | P1 | Positive | POS authenticated | N/A | 1. View prices in POS 2. Check format | All prices display in Rp XXX.XXX format
TC-POS-009 | POS | POS performance — page loads under 2.5s | P1 | Performance | Network monitoring enabled | N/A | 1. Measure POS page load time | FCP < 2,500ms
TC-POS-010 | POS | POS works on tablet/iPad viewport | P2 | Positive | Tablet viewport (768x1024) | N/A | 1. Open POS on tablet 2. Test functionality | POS fully functional on tablet display
TC-SEC-001 | Security | CSP header present in all responses | P1 | Security | Network monitoring enabled | N/A | 1. Open DevTools Network tab 2. Check response headers | Content-Security-Policy header present
TC-SEC-002 | Security | X-Frame-Options header present | P1 | Security | Network monitoring enabled | N/A | 1. Open DevTools Network tab 2. Check response headers | X-Frame-Options: DENY or SAMEORIGIN
TC-SEC-003 | Security | X-Content-Type-Options header present | P1 | Security | Network monitoring enabled | N/A | 1. Open DevTools Network tab 2. Check response headers | X-Content-Type-Options: nosniff
TC-SEC-004 | Security | Server/X-Powered-By headers suppressed | P1 | Security | Network monitoring enabled | N/A | 1. Check response headers 2. Verify no Server or X-Powered-By | Headers not present in responses
TC-SEC-005 | Security | HSTS header present with adequate max-age | P1 | Security | Network monitoring enabled | N/A | 1. Check response headers 2. View HSTS max-age value | Strict-Transport-Security present with max-age >= 31536000

## Summary Dashboard
Flexology v3 - QA Findings Summary
Findings by Severity |  | Findings by Area |  | Findings by Category
Severity | Count | Area | Count | Category | Count
Critical | 6 | Consumer | 7 | Performance | 2
High | 7 | Admin | 11 | Security | 3
Medium | 8 | POS | 1 | Functional | 6
Low | 4 | All | 6 | UX | 9
|  |  |  | Data | 5
v2 Status
Status | Count
New | 17
Open | 7
Partial fix | 1
Total Findings | 25

## Quick Wins
ID | Title | Severity | Area | Recommendation
V3-004 | Add security headers (CSP, X-Frame, etc.) | Critical | All | Add security headers via Next.js middleware or vercel.json headers config.
V3-005 | Remove tech stack headers (Server, X-Powered-By) | Critical | All | Configure Vercel to suppress Server header, remove X-Powered-By in next.config.js with poweredByHeader: false.
V3-007 | Fix SEE ALL link on homepage | High | Consumer | Add proper href or onClick handler to "SEE ALL" link targeting /services page.
V3-009 | Fix naming mismatches in admin pages | High | Admin | Align sidebar labels with page titles across all admin pages.
V3-014 | Capitalize therapist name Indra | Medium | Admin | Capitalize "indra" to "Indra" in database.
V3-015 | Clear staff form placeholder data | Medium | Admin | Clear placeholder values in new staff form on component mount.
V3-016 | Fix Confirm Booking button overlap | Medium | Consumer | Move Confirm Booking button below Contact Details, or make page scrollable.
V3-017 | Standardize time format to colons | Medium | Admin | Standardize time format to colons (09:00) across all admin pages.
V3-018 | Fix decimal format in credit card rate | Medium | Admin | Use period decimal (0.02) consistent with international standard.
V3-020 | Add Pondok Indah to leaderboard | Medium | Admin | Include all outlets (including Pondok Indah) in leaderboard query.
V3-022 | Fix scarcity indicator | Low | Consumer | Make scarcity indicator dynamic based on real-time data, or remove.
V3-024 | Fix login field label | Low | Consumer | Create separate admin login flow or relabel field to "ID / Mobile Number".
V3-025 | Customize 404 page | Low | All | Customize 404 page with Flexology branding and helpful navigation.