## All Findings
ID | Category | Severity | Title | v3 Claim | v4 Status | Description | Recommended Fix | Priority | Effort | Module
V3-001 | Performance | Critical | FCP 51,176ms (28x over target) | Claimed: Midtrans lazyOnload | NOT FIXED — REGRESSED | FCP worsened from 13,232ms to 51,176ms. 28x above 1,800ms target. | Profile critical rendering path. Defer render-blocking JS. Implement SSR/SSG for initial HTML shell. Code-split with next/dynamic. Lazy load below-fold components. Check for new dependencies added since v3. Target: FCP < 1,800ms. | P0 | Major | Consumer
V3-002 | Performance | Critical | Homepage TTFB 3,882ms (4.9x target) | Claimed: Stripped next/dynamic chunking | NOT FIXED | TTFB 3,882ms (slight improvement from 4,339ms). Only homepage affected. | Check getServerSideProps or server component data fetching. Add edge caching or ISR for homepage. Ensure no blocking API calls in server render. Check Vercel function logs for cold starts. | P0 | Major | Consumer
V3-003 | Functionality | Critical | POS system does not exist | Claimed: Built POS with offline/manual payment | NOT FIXED | /pos, /admin/pos, /terminal, /admin/terminal all return 404 | Build POS module: daily bookings view, check-in, walk-in booking, payment processing, receipt generation. Add POS link to admin sidebar. Implement outlet-scoped access. | P0 | Major | POS
V3-004 | Security | Critical | 5 security headers missing (4th audit cycle) | Claimed: middleware.ts injecting headers | NOT FIXED | CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy all MISSING | Add headers in next.config.js async headers() or middleware.ts. Verify deployment includes the middleware file. Check if vercel.json is overriding headers. | P0 | Quick Win | Platform
V3-005 | Security | Critical | Server/X-Powered-By exposed | Claimed: Removed X-Powered-By | NOT FIXED | Server: Vercel and X-Powered-By: Next.js still present | Set poweredByHeader: false in next.config.js. Configure Vercel project settings or middleware to strip Server header. | P0 | Quick Win | Platform
V3-006 | Security | Critical | Admin no-auth access | Claimed: Credentials rotated, middleware restrictions | NOT FIXED | Admin panel loads without login redirect after clearing all storage. No authentication middleware active. | Implement server-side session validation middleware. Use httpOnly secure cookies. Add rate limiting (5 attempts = 15min lockout). Require strong passwords. Implement MFA. | P0 | Major | Admin
V4-001 | Performance | Critical | FCP Critical Regression 3.9x worse | NEW FINDING | NEW | FCP degraded from 13,232ms (v3) to 51,176ms (v4). Most severe performance regression across all audit cycles. | Same as V3-001. Additionally investigate what changed between v3 and v4 deployments. Check git diff for new dependencies or removed optimizations. | P0 | Major | Consumer
V4-003 | Security | Critical | Admin panel authentication bypass | NEW FINDING | NEW | Admin panel accessible without any authentication after clearing all browser storage. Middleware auth appears non-functional. | Verify middleware.ts is deployed and executing. Check Vercel function logs for middleware invocation. Ensure matcher patterns include /admin routes. | P0 | Major | Admin
V3-007 | Functionality | High | SEE ALL link doesn't navigate | Claimed: Hard-wired to /services | PARTIAL | href="/book" but click doesn't trigger navigation from homepage | Fix Next.js Link component implementation. Check for e.preventDefault() calls. Ensure proper client-side routing. Link should point to /services (once built). | P1 | Quick Win | Consumer
V3-009 | UX | High | 3 naming mismatches sidebar vs page | Claimed: Resolved naming alignments | NOT FIXED | "Bookings Pipeline" vs "Operations Pipeline", "Staff Registry" vs "Staff Roster Setup", "Outlets & Managers" vs "Outlets & Operations" | Choose one name per section. Update sidebar component and page titles to match. | P1 | Quick Win | Admin
V3-010 | Functionality | High | Pipeline grid "No grid columns" | Claimed: Dynamic staff pulling by locationId | NOT FIXED | Schedule grid shows no therapist columns despite 2 active therapists | Query assigned staff for selected outlet. Render as grid columns. Place bookings in correct staff column at correct time slot. | P1 | Moderate | Admin
V3-011 | Data Integrity | High | Revenue shows Rp 0 | Claimed: Recalculated backend logic | NOT FIXED | Gross Settled Revenue "Rp 0" while leaderboard shows Rp 475,000 + Rp 400,000 = Rp 875,000 | Debug revenue aggregation query. Ensure "settled" status includes completed/paid bookings. Compare with working leaderboard query. | P1 | Moderate | Admin
V3-012 | Data Integrity | High | Currency 3 different formats | Claimed: Universal locale id-ID | NOT FIXED | Consumer: "IDR 200K", Admin: "Rp 0", Leaderboard: "Rp 475,000" (comma). Indonesian standard: "Rp 475.000" (period) | Create shared formatCurrency(amount) utility returning Rp + toLocaleString('id-ID'). Apply everywhere. Remove all hardcoded formatting. | P1 | Moderate | Platform
V3-013 | Functionality | High | /services page returns 404 | Claimed: Built dedicated /services page | NOT FIXED | /services returns 404 Not Found. No services browsing page exists. | Create /services page listing all services across all outlets with filtering by type. Show name, duration, price, description, rating. | P1 | Moderate | Consumer
V4-002 | Functionality | High | Sign Out button non-functional | NEW FINDING | NEW | Clicking Sign Out in admin doesn't log out or redirect. User stays on dashboard. | Debug Sign Out form submission. Ensure it clears server-side session. Add redirect to homepage or login after signout. | P1 | Quick Win | Admin
V3-014 | Data Integrity | Medium | Therapist "indra" not capitalized | Claimed: DB sanitized | NOT FIXED | Still shows "indra" in staff registry | Run DB migration to capitalize: UPDATE therapists SET name = 'Indra' WHERE name = 'indra'. Add name validation on input. | P2 | Quick Win | Admin
V3-015 | UX | Medium | Pre-filled staff form "Sarah Jenkins" | Claimed: Not specified | NOT FIXED | Add Therapist form shows "Sarah Jenkins" and "Sports Massage, Recovery" | Replace pre-filled values with empty inputs or proper placeholder attributes. | P2 | Quick Win | Admin
V3-017 | Data Integrity | Medium | Time format uses periods (08.00) | Claimed: Not specified | NOT FIXED | Outlets page shows "08.00" and "22.00" with periods instead of colons | Standardize time display to HH:MM format with colons across all pages. | P2 | Quick Win | Admin
V3-018 | Data Integrity | Medium | Credit card rate comma decimal (0,02) | Claimed: Sanitized via replace() | NOT FIXED | System Variables shows "0,02" instead of "0.02" | Ensure numeric inputs use period decimal separator. Apply locale-aware parsing or force standard decimal notation. | P2 | Quick Win | Admin
V3-020 | Data Integrity | Medium | Pondok Indah missing from leaderboard | Claimed: Outlets instantiate Volume: 0 | NOT FIXED | Only Home Service and Dash Padel in leaderboard | Include all outlets in leaderboard query even with 0 sessions. Use LEFT JOIN or similar to ensure completeness. | P2 | Moderate | Admin
V3-021 | Data Integrity | Medium | Staff assignment inconsistency | Claimed: Properly binds staff records | PARTIAL | Widi and indra assigned to Pondok Indah but dispatched for Home Service | Reconcile location assignments in DB. Ensure booking flow reflects actual staff location. | P2 | Moderate | Admin
V3-016 | UX | Medium | Contact details hidden behind keyboard | Claimed: Expanded padding pb-[200px] | NOT VERIFIED | Booking summary Contact Details may be obscured by Confirm button | Verify on mobile viewport. Ensure sticky button doesn't overlap form content. Add scroll padding. | P2 | Quick Win | Consumer
V3-019 | Functionality | Medium | Therapist not filtered by specialty | Claimed: Selection algorithms scan specialty | NOT VERIFIED | Selecting Assisted Stretching may show Sports Massage therapists | Filter therapist list by matching service specialty. Only show qualified therapists. | P2 | Moderate | Consumer
V3-023 | UX | Low | No responsive desktop layout | Claimed: Maintained max-w-[480px] | NOT FIXED | App renders as fixed mobile-width container on all screens | Add responsive breakpoints. Use max-w-lg or similar for tablet, full-width grid for desktop. | P3 | Major | Consumer
V3-025 | UX | Low | Generic 404 page | Claimed: Custom "Lost in the Void" deployed | NOT FIXED | Still shows "The wellness therapy or page you are looking for has been removed..." | Deploy the custom not-found.tsx. Add Flexology branding, helpful navigation links, search suggestions. | P3 | Quick Win | Platform
V3-024 | UX | Low | Login label confusion | Claimed: Expanded to "ID / Mobile Number" | NOT VERIFIED | Admin login field may still say "MOBILE NUMBER" | Change label to "ID / Mobile Number" or create separate admin login route. | P3 | Quick Win | Admin

## Test Cases
TC-ID | Module | Title | Priority | Type | Preconditions | Test Steps | Expected Result
TC-PERF-001 | Consumer | Measure First Contentful Paint (FCP) | P0 | Performance | Clean browser cache, no throttling | 1. Navigate to homepage 2. Open DevTools Performance tab 3. Record page load 4. Measure FCP metric | FCP should be < 1,800ms. Current: 51,176ms (FAILED)
TC-PERF-002 | Consumer | Measure Time to First Byte (TTFB) | P0 | Performance | Clean cache, slow 3G simulation | 1. Navigate to homepage 2. Enable Network throttling (Slow 3G) 3. Record load time 4. Measure TTFB | TTFB should be < 800ms. Current: 3,882ms (FAILED)
TC-PERF-003 | Consumer | Test booking page load performance | P1 | Performance | User logged in, service selected | 1. Navigate to booking page 2. Record performance metrics 3. Measure LCP and INP | LCP < 2.5s, INP < 200ms
TC-PERF-004 | Admin | Measure admin dashboard load time | P1 | Performance | Admin authenticated, cache clear | 1. Login to admin 2. Navigate to dashboard 3. Record page load metrics | Initial load < 3 seconds
TC-PERF-005 | Consumer | Test booking confirmation page performance | P1 | Performance | Booking in progress, all data loaded | 1. Proceed to confirmation 2. Measure rendering time 3. Check for layout shifts | No CLS > 0.1, FCP < 2.5s
TC-PERF-006 | Admin | Test pipeline grid rendering with 20+ bookings | P1 | Performance | Outlet selected, bookings loaded | 1. Load Bookings Pipeline with 20+ entries 2. Measure render time 3. Check for scrolling lag | Grid renders in < 2s, scroll FPS > 50
TC-PERF-007 | Consumer | Test image loading performance on services page | P1 | Performance | Services page loaded | 1. Open /services page 2. Measure image load times 3. Check lazy loading | Images load progressively, LCP < 2.5s
TC-PERF-008 | Admin | Test leaderboard calculation and render time | P1 | Performance | Multiple outlets with data | 1. Open Leaderboard 2. Measure data fetch and render 3. Check sort performance | Render < 1.5s, sort < 500ms
TC-SEC-001 | Platform | Verify Content Security Policy header | P0 | Security | Browser DevTools open | 1. Open DevTools Network tab 2. Navigate to any page 3. Check response headers | CSP header should be present and properly configured
TC-SEC-002 | Platform | Verify X-Frame-Options header | P0 | Security | Browser DevTools open | 1. Check response headers for X-Frame-Options 2. Try to iframe the page in another domain | X-Frame-Options: DENY or SAMEORIGIN should be set
TC-SEC-003 | Platform | Verify Server header not exposed | P0 | Security | Browser DevTools open | 1. Make request to any page 2. Check response headers 3. Look for Server header | Server header should be stripped or generic
TC-SEC-004 | Platform | Verify X-Powered-By header removed | P0 | Security | Network tab available | 1. Make HTTP request 2. Check response headers 3. Look for X-Powered-By | X-Powered-By should not be exposed
TC-SEC-005 | Admin | Admin authentication bypass attempt | P0 | Security | Fresh browser, admin URL known | 1. Clear all browser storage 2. Navigate directly to /admin 3. Attempt to access dashboard without login | Should redirect to login page
TC-SEC-006 | Admin | Test session timeout | P1 | Security | Admin logged in, timer available | 1. Login to admin 2. Wait for session timeout (or manually expire) 3. Try to perform action | Should redirect to login
TC-SEC-007 | Admin | Test password strength validation | P1 | Security | Login page available | 1. Attempt to set weak password 2. Try common passwords 3. Verify min length requirement | Weak passwords should be rejected
TC-SEC-008 | Admin | Test rate limiting on login attempts | P1 | Security | Login page available | 1. Make 5+ failed login attempts 2. Measure lockout duration 3. Verify error message | Should lock after 5 attempts for 15 minutes
TC-SEC-009 | Platform | Verify HTTPS enforcement | P1 | Security | Network tools available | 1. Try to access via HTTP 2. Check for redirect to HTTPS 3. Verify HSTS header | Should enforce HTTPS with HSTS header
TC-SEC-010 | Platform | Verify Referrer-Policy and Permissions-Policy | P1 | Security | Browser DevTools open | 1. Check response headers 2. Look for Referrer-Policy and Permissions-Policy 3. Verify restrictive settings | Both headers should be present and secure
TC-FUNC-001 | Consumer | Test homepage SEE ALL link navigation | P1 | Functional | Homepage loaded, link visible | 1. Click 'SEE ALL' link on homepage 2. Observe navigation | Should navigate to /services page
TC-FUNC-002 | Consumer | Test booking flow from homepage | P1 | Functional | Homepage loaded, services available | 1. Select a service 2. Choose therapist and time 3. Proceed to booking | Should complete booking without errors
TC-FUNC-003 | POS | Test POS module access | P0 | Functional | Admin authenticated, POS role assigned | 1. Navigate to /pos 2. Attempt to access POS dashboard | /pos should load with POS interface
TC-FUNC-004 | POS | Test POS daily bookings view | P0 | Functional | POS module loaded, bookings exist | 1. View daily bookings 2. Check therapist assignments 3. Verify walk-in booking option | Should display all daily bookings with therapist and time
TC-FUNC-005 | POS | Test POS check-in functionality | P0 | Functional | Booking exists in system | 1. Select a booking 2. Click Check In 3. Verify status change | Booking status should change to checked-in
TC-FUNC-006 | POS | Test POS walk-in booking creation | P0 | Functional | POS interface loaded, therapist available | 1. Click 'Add Walk-In' 2. Select service and therapist 3. Complete booking | Walk-in booking should be created and visible
TC-FUNC-007 | POS | Test POS payment processing | P0 | Functional | Booking ready for payment | 1. Select payment method 2. Process payment 3. Verify receipt generation | Payment should process and receipt should display
TC-FUNC-008 | Consumer | Test /services page loading | P1 | Functional | Services page URL known | 1. Navigate to /services 2. Wait for page load 3. Verify service list displays | /services should load with complete service list
TC-FUNC-009 | Admin | Test admin sign out functionality | P1 | Functional | Admin logged in, sign out button visible | 1. Click Sign Out button 2. Observe redirect 3. Verify session cleared | Should redirect to homepage and clear authentication
TC-FUNC-010 | Admin | Test Bookings Pipeline grid population | P1 | Functional | Pipeline page loaded, outlet selected | 1. Select an outlet with therapists 2. View pipeline grid 3. Check therapist columns | Grid should show therapist columns with their bookings
TC-FUNC-011 | Admin | Test pipeline booking placement | P1 | Functional | Bookings exist, pipeline loaded | 1. Create a booking 2. View in pipeline 3. Verify correct staff column | Booking should appear in correct staff and time slot
TC-FUNC-012 | Admin | Test revenue calculation | P1 | Functional | Multiple completed bookings exist | 1. Navigate to revenue dashboard 2. Check Gross Settled Revenue 3. Compare with leaderboard | Revenue should match leaderboard total
TC-FUNC-013 | Admin | Test outlet selection filter | P1 | Functional | Multiple outlets configured | 1. Select different outlets 2. Verify data changes per outlet 3. Check assignment accuracy | Data should filter correctly by outlet
TC-FUNC-014 | Admin | Test therapist assignment to outlet | P1 | Functional | Staff registry loaded | 1. Assign therapist to outlet 2. Save assignment 3. Verify in pipeline | Therapist should appear in correct outlet pipeline
TC-FUNC-015 | Consumer | Test booking with service specialty match | P1 | Functional | Booking page loaded, services available | 1. Select service (e.g., Assisted Stretching) 2. View available therapists 3. Verify specialty match | Only qualified therapists should be available
TC-FUNC-016 | Admin | Test leaderboard data accuracy | P1 | Functional | Multiple outlets with bookings | 1. Check leaderboard totals 2. Verify all outlets included 3. Confirm calculations | All outlets should appear with correct revenue
TC-FUNC-017 | Consumer | Test booking confirmation email | P1 | Functional | Booking completed | 1. Complete booking 2. Check email inbox 3. Verify content | Confirmation email should be received within 1 minute
TC-FUNC-018 | Admin | Test therapist filter by specialty | P1 | Functional | Staff registry loaded, specialties assigned | 1. Filter staff by specialty 2. View filtered list 3. Verify accuracy | Only therapists with specialty should display
TC-FUNC-019 | Admin | Test staff registry CRUD operations | P1 | Functional | Admin access granted | 1. Create new therapist 2. Edit details 3. Verify save | All CRUD operations should work without errors
TC-FUNC-020 | Admin | Test outlet and outlet manager assignment | P1 | Functional | Outlets configured | 1. Assign manager to outlet 2. Verify access control 3. Check manager permissions | Manager should only access assigned outlet
TC-DATA-001 | Admin | Verify therapist name capitalization | P2 | Data Integrity | Staff registry loaded | 1. Check staff names in database 2. Verify capitalization 3. Look for 'indra' vs 'Indra' | All therapist names should be properly capitalized
TC-DATA-002 | Admin | Verify currency format consistency - IDR | P1 | Data Integrity | Admin dashboard loaded, revenue data visible | 1. Check revenue display 2. Check leaderboard 3. Check consumer bookings | All should use 'Rp' prefix with id-ID locale formatting
TC-DATA-003 | Admin | Verify decimal separator in prices | P2 | Data Integrity | System Variables page loaded | 1. Check credit card rates 2. Verify decimal separator 3. Test input and display | Should use period (.) not comma (,) for decimals
TC-DATA-004 | Admin | Verify time format consistency | P2 | Data Integrity | Outlets page and pipeline loaded | 1. Check outlet operating hours 2. Check booking times 3. Check system times | All times should use HH:MM format with colons
TC-DATA-005 | Admin | Verify staff outlet assignments | P2 | Data Integrity | Pipeline and staff registry loaded | 1. Check assigned therapists 2. Verify outlet match 3. Check booking assignments | Staff should be assigned only to their outlet
TC-DATA-006 | Admin | Verify all outlets in leaderboard | P2 | Data Integrity | Leaderboard page loaded | 1. Count outlets in database 2. Count outlets in leaderboard 3. Verify all included | All outlets should appear even with 0 revenue
TC-DATA-007 | Admin | Verify booking status consistency | P2 | Data Integrity | Multiple bookings exist with different statuses | 1. Create and complete bookings 2. Check status transitions 3. Verify in all views | Status should be consistent across all views
TC-DATA-008 | Admin | Verify revenue aggregation accuracy | P1 | Data Integrity | Multiple completed bookings exist | 1. Sum manual calculations 2. Compare with system total 3. Verify settled vs unsettled | Revenue totals should match manual calculations
TC-DATA-009 | Consumer | Verify booking summary data accuracy | P1 | Data Integrity | Booking in confirmation stage | 1. Review booking details 2. Verify therapist name 3. Check time and date | All details should match selected values
TC-DATA-010 | Admin | Verify therapist specialty assignments | P2 | Data Integrity | Staff registry loaded with specialties | 1. Check specialty for each therapist 2. Verify consistency 3. Match with services | Specialties should match offered services
TC-DATA-011 | Consumer | Verify price calculation on booking | P1 | Data Integrity | Booking with service selection | 1. Select service with known price 2. Check displayed price 3. Verify currency format | Price should be correct and properly formatted
TC-DATA-012 | Admin | Verify leaderboard calculations | P2 | Data Integrity | Multiple outlets with bookings | 1. Calculate manual totals 2. Compare with leaderboard 3. Check aggregation logic | Calculations should match across all outlets
TC-UX-001 | Admin | Verify sidebar naming consistency | P1 | UX | Admin dashboard loaded | 1. Check sidebar labels 2. Check page titles 3. Compare for consistency | Sidebar and page titles should match
TC-UX-002 | Admin | Verify form field clearing on reload | P2 | UX | Add Staff form loaded | 1. Check pre-filled values in form 2. Clear and reload 3. Verify clean state | Form should have empty inputs, no pre-filled values
TC-UX-003 | Consumer | Verify contact details visibility on mobile | P2 | UX | Booking confirmation on mobile viewport | 1. Open booking confirmation 2. Scroll to Contact Details 3. Check button overlap | Contact Details should not be hidden by buttons
TC-UX-004 | Consumer | Verify 404 page branding and UX | P3 | UX | Navigate to non-existent page | 1. Go to invalid URL 2. Check page design 3. Verify navigation options | Should show custom 404 with helpful links
TC-UX-005 | Consumer | Verify responsive layout on desktop | P3 | UX | Desktop viewport (1920x1080) | 1. Open homepage 2. Check layout responsiveness 3. Verify content width | Should use full width, not fixed mobile container
TC-UX-006 | Admin | Verify login field label clarity | P3 | UX | Admin login page | 1. Check login field label 2. Verify clarity for mobile/ID input 3. Test input types | Label should be 'ID / Mobile Number'
TC-UX-007 | Consumer | Verify booking flow messaging | P1 | UX | Complete booking flow | 1. Navigate through booking steps 2. Check confirmation messages 3. Verify clarity | All messages should be clear and actionable
TC-UX-008 | Admin | Verify dashboard navigation clarity | P1 | UX | Admin dashboard loaded | 1. Identify navigation elements 2. Check label consistency 3. Verify intuitive layout | Navigation should be clear and consistent
TC-UX-009 | Consumer | Verify error message clarity | P2 | UX | Complete booking with errors | 1. Trigger various errors 2. Check error messages 3. Verify solution guidance | Error messages should be clear and suggest fixes
TC-UX-010 | Consumer | Verify service information completeness | P2 | UX | Services page loaded | 1. Check service details 2. Verify ratings/reviews 3. Check description completeness | All service info should be complete and readable
TC-REG-001 | Consumer | Regression: Booking flow still functional | P1 | Regression | Services and therapists available | 1. Complete full booking flow 2. Verify all steps work 3. Check confirmation | Booking should complete without errors
TC-REG-002 | Admin | Regression: Sports Massage spelling correct | P2 | Regression | Staff specialty list loaded | 1. Check specialty list 2. Search for 'Sports Massage' 3. Verify spelling | Should be 'Sports Massage' not 'Sports Massage'
TC-REG-003 | Platform | Regression: HSTS header present | P1 | Regression | Network DevTools available | 1. Check response headers 2. Look for HSTS 3. Verify max-age | HSTS header should be present and valid
TC-REG-004 | Admin | Regression: Sidebar navigation working | P1 | Regression | Admin dashboard loaded | 1. Click each sidebar link 2. Verify navigation 3. Check page changes | All sidebar navigation should work
TC-REG-005 | Consumer | Regression: Booking confirmation email sending | P1 | Regression | Email system functional | 1. Complete booking 2. Check email 3. Verify content | Confirmation email should be sent automatically

## Summary Dashboard
Flexology v4 Audit - Summary Dashboard
Findings by Severity
Critical | High | Medium | Low | Total
8 | 7 | 8 | 3 | 26
Findings by Status
NOT FIXED | PARTIAL | NEW | NOT VERIFIED | FIXED
18 | 2 | 3 | 3 | 0
Findings by Module |  |  | Findings by Category
Module | Count |  | Category | Count
Consumer | 8 |  | Performance | 3
Admin | 13 |  | Security | 4
POS | 1 |  | Functionality | 6
Platform | 4 |  | Data Integrity | 7
|  |  | UX | 6
Deployment Readiness Score
Category | Score (/10)
Performance | 0.1
Security | 0.2
Functionality | 0.5
UX | 0.5
Data Integrity | 0.3
OVERALL | 0.32

## Quick Wins
ID | Category | Severity | Title | v3 Claim | v4 Status | Description | Recommended Fix | Priority | Effort | Module
V3-004 | Security | Critical | 5 security headers missing (4th audit cycle) | Claimed: middleware.ts injecting headers | NOT FIXED | CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy all MISSING | Add headers in next.config.js async headers() or middleware.ts. Verify deployment includes the middleware file. Check if vercel.json is overriding headers. | P0 | Quick Win | Platform
V3-005 | Security | Critical | Server/X-Powered-By exposed | Claimed: Removed X-Powered-By | NOT FIXED | Server: Vercel and X-Powered-By: Next.js still present | Set poweredByHeader: false in next.config.js. Configure Vercel project settings or middleware to strip Server header. | P0 | Quick Win | Platform
V3-007 | Functionality | High | SEE ALL link doesn't navigate | Claimed: Hard-wired to /services | PARTIAL | href="/book" but click doesn't trigger navigation from homepage | Fix Next.js Link component implementation. Check for e.preventDefault() calls. Ensure proper client-side routing. Link should point to /services (once built). | P1 | Quick Win | Consumer
V3-009 | UX | High | 3 naming mismatches sidebar vs page | Claimed: Resolved naming alignments | NOT FIXED | "Bookings Pipeline" vs "Operations Pipeline", "Staff Registry" vs "Staff Roster Setup", "Outlets & Managers" vs "Outlets & Operations" | Choose one name per section. Update sidebar component and page titles to match. | P1 | Quick Win | Admin
V4-002 | Functionality | High | Sign Out button non-functional | NEW FINDING | NEW | Clicking Sign Out in admin doesn't log out or redirect. User stays on dashboard. | Debug Sign Out form submission. Ensure it clears server-side session. Add redirect to homepage or login after signout. | P1 | Quick Win | Admin
V3-014 | Data Integrity | Medium | Therapist "indra" not capitalized | Claimed: DB sanitized | NOT FIXED | Still shows "indra" in staff registry | Run DB migration to capitalize: UPDATE therapists SET name = 'Indra' WHERE name = 'indra'. Add name validation on input. | P2 | Quick Win | Admin
V3-015 | UX | Medium | Pre-filled staff form "Sarah Jenkins" | Claimed: Not specified | NOT FIXED | Add Therapist form shows "Sarah Jenkins" and "Sports Massage, Recovery" | Replace pre-filled values with empty inputs or proper placeholder attributes. | P2 | Quick Win | Admin
V3-017 | Data Integrity | Medium | Time format uses periods (08.00) | Claimed: Not specified | NOT FIXED | Outlets page shows "08.00" and "22.00" with periods instead of colons | Standardize time display to HH:MM format with colons across all pages. | P2 | Quick Win | Admin
V3-018 | Data Integrity | Medium | Credit card rate comma decimal (0,02) | Claimed: Sanitized via replace() | NOT FIXED | System Variables shows "0,02" instead of "0.02" | Ensure numeric inputs use period decimal separator. Apply locale-aware parsing or force standard decimal notation. | P2 | Quick Win | Admin
V3-016 | UX | Medium | Contact details hidden behind keyboard | Claimed: Expanded padding pb-[200px] | NOT VERIFIED | Booking summary Contact Details may be obscured by Confirm button | Verify on mobile viewport. Ensure sticky button doesn't overlap form content. Add scroll padding. | P2 | Quick Win | Consumer
V3-025 | UX | Low | Generic 404 page | Claimed: Custom "Lost in the Void" deployed | NOT FIXED | Still shows "The wellness therapy or page you are looking for has been removed..." | Deploy the custom not-found.tsx. Add Flexology branding, helpful navigation links, search suggestions. | P3 | Quick Win | Platform
V3-024 | UX | Low | Login label confusion | Claimed: Expanded to "ID / Mobile Number" | NOT VERIFIED | Admin login field may still say "MOBILE NUMBER" | Change label to "ID / Mobile Number" or create separate admin login route. | P3 | Quick Win | Admin