## All Findings
ID | Category | Title | Description | Severity | Status | V8 Status | Cycles Open | Owner | Recommendation
V9-M01 | Performance | Homepage FCP 11.9s | Improved from 48.6s but still 6.6x above 1800ms target. TTFB 3631ms. | High | Partial | Was Critical | 5 (V5-V9) | Dev | Further optimize GSAP lazy loading, add Vercel warming
V9-M02 | Data | Revenue Dashboard | KPI Rp 475.000 matches leaderboard sum |  | Fixed | Was Critical | Resolved |  | No action
V9-M03 | Security | Credential Blocklist | 0000/admin blocked but causes server crash, infinite spinner, credentials in URL | Critical | Partial | Was Critical | 5 (V5-V9) | Dev | Return clean error response, use POST not GET for login
V9-M04 | UX | Booking Visual Feedback | Checkmark, border, aria-pressed working |  | Fixed | Was High | Resolved |  | No action
V9-M05 | Security | Security Headers | All 6 headers present (CSP, XFO, XCTO, RP, PP, HSTS) |  | Fixed | Was High | Resolved |  | No action
V9-M06 | Security | XSS Sanitization | Server crash on XSS input instead of clean rejection | High | Partial | Was High | 3 (V7-V9) | Dev | Add try-catch around sanitizer, return validation error
V9-M07 | Security | Rate Limiting | Cannot verify — login crashes before rate limiter executes | Medium | Inconclusive | Was High | 3 (V7-V9) | Dev | Fix login crash first, then retest
V9-M08 | UX | Password Toggle | Eye icon on login and register |  | Fixed | Was Medium | Resolved |  | No action
V9-M09 | Feature | POS in Sidebar | Link present, navigates to placeholder |  | Fixed | Was Medium | Resolved |  | Build POS module
V9-M10 | UX | Currency Format | Partially fixed. Booking correct, KPI shows "4,00" for integers | Low | Partial | Was Low | 3 (V7-V9) | Dev | Use Math.round for integer counts
V9-M11 | Security | Session/Auth | Admin accessible WITHOUT login via direct URL | Critical | Regressed | Was High | 2 (V8-V9) | Dev | Fix middleware matcher, add auth check
V9-M12 | Build | Version Mismatch | Admin shows v0.9.1, report claims v0.9.3 | Low | New | N/A | 1 | Dev | Verify build pipeline
V9-N01 | Stability | Admin Pages 500 | /staff, /settings, /outlets return 500 errors | Critical | New | N/A | 1 | Dev | Debug server components on these routes
V9-N02 | Security | Credentials in URL | Login redirects to /login?phone=X&password=Y | Critical | New | N/A | 1 | Dev | Use POST method, never put credentials in URL
V9-N03 | Stability | Server Component Crashes | Unhandled errors on login block + registration sanitize | High | New | N/A | 1 | Dev | Add error boundaries and try-catch
V9-N04 | Security | Admin No Auth Required | /admin loads full dashboard without any authentication | Critical | New | N/A | 1 | Dev | Fix middleware to enforce auth
V9-N05 | Stability | Profile 500 Error | /profile returns 500 error | High | New | N/A | 1 | Dev | Fix server component
V9-N06 | Feature | Rewards Redirect | /rewards redirects to homepage | Medium | New | N/A | 1 | Dev | Fix rewards page routing

## V5-V9 Trend
Audit | Score | Critical | High | Medium | Low | Fixed
V5 | 5.8 | 2 | 3 | 2 | 1 | 0
V6 | 3.2 | 3 | 4 | 2 | 1 | 0
V7 | 4.5 | 3 | 5 | 2 | 2 | 1
V8 | 3.8 | 3 | 5 | 2 | 2 | 1
V9 | 4.3 | 4 | 4 | 2 | 2 | 6

## Quick Wins
ID | Category | Title | Description | Severity | Status | V8 Status | Cycles Open | Owner | Recommendation
V9-M04 | UX | Booking Visual Feedback | Checkmark, border, aria-pressed working |  | Fixed | Was High | Resolved |  | No action
V9-M05 | Security | Security Headers | All 6 headers present (CSP, XFO, XCTO, RP, PP, HSTS) |  | Fixed | Was High | Resolved |  | No action
V9-M08 | UX | Password Toggle | Eye icon on login and register |  | Fixed | Was Medium | Resolved |  | No action
V9-M09 | Feature | POS in Sidebar | Link present, navigates to placeholder |  | Fixed | Was Medium | Resolved |  | Build POS module

## Improvement Roadmap
Phase | Finding ID | Title | Severity | Owner | Timeline
Phase 1: Critical | V9-M03 | Credential Blocklist | Critical | Dev | Immediate
Phase 1: Critical | V9-N01 | Admin Pages 500 | Critical | Dev | Immediate
Phase 1: Critical | V9-N02 | Credentials in URL | Critical | Dev | Immediate
Phase 1: Critical | V9-N04 | Admin No Auth Required | Critical | Dev | Immediate
Phase 1: Critical | V9-M11 | Session/Auth | Critical | Dev | Immediate
Phase 2: High | V9-M01 | Homepage FCP 11.9s | High | Dev | Week 1
Phase 2: High | V9-M06 | XSS Sanitization | High | Dev | Week 1
Phase 2: High | V9-N03 | Server Component Crashes | High | Dev | Week 1
Phase 2: High | V9-N05 | Profile 500 Error | High | Dev | Week 1
Phase 3: Polish | V9-M07 | Rate Limiting | Medium | Dev | Week 2
Phase 3: Polish | V9-M10 | Currency Format | Low | Dev | Week 2
Phase 3: Polish | V9-N06 | Rewards Redirect | Medium | Dev | Week 2

## Summary Dashboard
Flexology V9 Audit Summary
Total Findings: | 18
Critical Issues: | 5
High Issues: | 4
Medium Issues: | 2
Low Issues: | 2
Fixed Items: | 5
Overall Score: | 4.3