## All Findings
ID | Pillar | Category | Title | Description | Severity | Impact | Effort | Priority | Status | Recommendation | Verified Against V4 Report
V5-001 | Functional | POS Module | POS System Returns 404 | The /pos endpoint returns "Not Found" error. No POS link exists in admin sidebar navigation. Verification report V3-003 claimed this was fixed but it is not deployed. | Critical | Users cannot access POS at all, blocking in-store operations | 2-4 hours | P1-BLOCKER | OPEN | Restore POS routing in middleware.ts, add POS link to admin sidebar component, verify GLOBAL_MANAGER and OUTLET_MANAGER roles have /pos access | REGRESSED from V3-003
V5-002 | Functional | Data Integrity | Revenue Data Mismatch | Executive Dashboard "Gross Settled Revenue" shows Rp 0 while Outlet Performance Leaderboard shows Rp 475,000 (Home Service) + Rp 400,000 (Dash Padel) = Rp 875,000 total. The totalRevenue reduction hook in admin/page.tsx is not aggregating correctly. | Critical | Financial reporting is inaccurate, undermines trust in admin dashboard | 2-3 hours | P1-BLOCKER | OPEN | Debug totalRevenue reduction hook inside outletMap volume calculation in admin/page.tsx. Ensure all outlet revenue data feeds into the KPI card. | NOT VERIFIED from V3-011
V5-003 | UX | Layout/Overflow | System Variables Page Scroll Bug | The /admin/settings page has a CSS overflow issue. Content below the Economy Engine section (Membership Tiers CRM) is cut off and inaccessible. Scrolling does not work. Body scrollHeight=2003 but viewport is 750px with scrollY stuck at 0. | Major | Admin cannot configure membership tiers or view/edit CRM settings | 1-2 hours | P1-BLOCKER | OPEN | Fix CSS overflow property on main content container. Likely needs overflow-y: auto on the correct parent element. Check for conflicting overflow: hidden rules. | REGRESSED from V3-016
V5-004 | UX | Naming Consistency | Sidebar vs Page Title Mismatch (x3) | Three admin sidebar labels don't match their page titles: "Bookings Pipeline" → page shows "Operations Pipeline", "Staff Registry" → page shows "Staff Roster Setup", "Outlets & Managers" → page shows "Outlets & Operations" | Medium | Confusing navigation, reduces user trust in admin panel professionalism | 1 hour | P2-HIGH | OPEN | Align either sidebar labels or page titles to be consistent. Recommended: update sidebar labels to match page titles. | PARTIALLY from V3-009
V5-005 | Security/UX | Form Data | Login Form Pre-filled with Test Data | Login page mobile number field shows "0812-3456-7890" and password shows dots (pre-filled). These appear to be test/placeholder values left in production code. | Medium | Security risk (exposes test credentials pattern), UX confusion for real users | 30 min | P2-HIGH | OPEN | Remove any default values from login form. Use placeholder text only, not actual field values. Check if this is a browser autofill issue vs hardcoded defaults. | NEW
V5-006 | Functional | Data Display | Grid vs Pipeline View Inconsistency | Operations Pipeline Grid view shows "No grid columns available" while Pipeline view shows a "PENDING MATCH" booking for "Ade S". The two views should display the same underlying data. | Major | Admin may miss pending bookings if only using Grid view, leading to unserviced customers | 2-3 hours | P2-HIGH | OPEN | Ensure Grid view queries the same data source as Pipeline view. "No grid columns" likely means no staff columns are rendered for the selected date/location, but bookings still exist. | PARTIALLY from V3-010/V3-021
V5-007 | UX | Format Consistency | Time Format Inconsistency | Shift times use dots in form inputs ("09.00") but colons on staff cards ("09:00 – 20:00") and outlet cards. Should use one format throughout. | Minor | Visual inconsistency reduces perceived quality | 1 hour | P3-MEDIUM | OPEN | Standardize all time displays to colon format (HH:MM) across admin panel. Update form input formatters. | PARTIALLY from V3-017/V3-018
V5-008 | UX | Format Consistency | Credit Card Rate Format Mismatch | System Variables shows Credit Card Rate value as "0,02" (comma decimal) but helper text says "e.g. 0.029 for 2.9%" (dot decimal). Indonesian locale uses comma but technical notation uses dot. | Minor | Could cause data entry errors if admin enters wrong format | 30 min | P3-MEDIUM | OPEN | Either enforce dot notation in the input or convert comma to dot on save. Update helper text to match expected input format. | PARTIALLY from V3-017
V5-009 | UX | Test Data | Staff Form Pre-filled with Sample Data | Add Therapist form on Staff Registry page shows pre-filled "Sarah Jenkins" in Full Name and "Sports Massage, Recovery" in Specialty. This is sample/placeholder data that shouldn't be in production. | Minor | Could accidentally create a fake staff member if admin clicks Create Profile without clearing fields | 15 min | P3-MEDIUM | OPEN | Clear all form fields on page load. Use placeholder text (grayed out) instead of actual field values. | NEW
V5-010 | UX | Empty States | Unhelpful Grid Empty State Message | Operations Pipeline Grid view displays "No grid columns available" which doesn't explain why or what to do. | Trivial | Minor UX friction for admin users | 30 min | P4-LOW | OPEN | Replace with descriptive message like "No staff scheduled at this location for today. Assign therapists in Staff Registry to see their schedules here." | NEW
V5-011 | UX | Accessibility | No Password Visibility Toggle | Login and Registration forms lack a show/hide password toggle (eye icon). | Trivial | Minor accessibility and usability friction | 1 hour | P4-LOW | OPEN | Add password visibility toggle button with eye/eye-off icon to password fields on login and register pages. | NEW
V5-012 | Performance | FCP/TTFB | Performance Recovery Confirmed | FCP recovered to 400-628ms (was 51s in V4). TTFB excellent at 311-375ms. All Core Web Vitals passing. | Info | Positive finding — no action needed | N/A | N/A | VERIFIED | Continue monitoring. Consider setting up RUM (Real User Monitoring) for production. | VERIFIED from V4-001/V3-002
V5-013 | Security | Authentication | Admin Auth Protection Working | Direct navigation to /admin without authentication correctly redirects to homepage/login. JWT validation appears functional. | Info | Positive finding — no action needed | N/A | N/A | VERIFIED | Maintain current authentication middleware. Consider adding audit logging for failed auth attempts. | VERIFIED from V4-003/V3-006
V5-014 | Security | Headers | Security Headers Partially Configured | Some security headers present but need verification of complete CSP, HSTS, X-Frame-Options, X-Content-Type-Options, Permissions-Policy deployment. Server/X-Powered-By headers should be suppressed. | Medium | Potential attack vectors if headers misconfigured | 2-4 hours | P2-HIGH | OPEN | Run curl -I against production URL. Verify all headers from V3-004/V3-005 are present. Test with securityheaders.com for grade. | PARTIALLY from V3-004/V3-005
V5-015 | Security | Session | Sign Out Flow Needs Validation | Sign Out button exists in admin sidebar but full flow (cookie deletion, session invalidation, redirect) not fully validated during this audit. | Low | Incomplete session termination could leave stale auth tokens | 1 hour | P3-MEDIUM | OPEN | Test full sign out flow: click Sign Out → verify flex_session cookie deleted → verify redirect to login → verify /admin returns 401/redirect. | NOT VERIFIED from V4-002

## Quick Wins
ID | Title | Severity | Effort | Recommendation
V5-005 | Login Form Pre-filled with Test Data | Medium | 30 min | Remove any default values from login form. Use placeholder text only, not actual field values.
V5-008 | Credit Card Rate Format Mismatch | Minor | 30 min | Either enforce dot notation in the input or convert comma to dot on save. Update helper text.
V5-009 | Staff Form Pre-filled with Sample Data | Minor | 15 min | Clear all form fields on page load. Use placeholder text (grayed out) instead of actual field values.
V5-004 | Sidebar vs Page Title Mismatch (x3) | Medium | 1 hour | Align either sidebar labels or page titles to be consistent. Update sidebar labels to match page titles.
V5-007 | Time Format Inconsistency | Minor | 1 hour | Standardize all time displays to colon format (HH:MM) across admin panel. Update form input formatters.

## Improvement Roadmap
Phase | ID | Title | Severity | Effort | Owner | Target Date | Status
Phase 1: IMMEDIATE (This Sprint) | V5-001 | POS System Returns 404 | Critical | 2-4 hours |  |  | OPEN
Phase 1: IMMEDIATE (This Sprint) | V5-002 | Revenue Data Mismatch | Critical | 2-3 hours |  |  | OPEN
Phase 1: IMMEDIATE (This Sprint) | V5-003 | System Variables Page Scroll Bug | Major | 1-2 hours |  |  | OPEN
Phase 2: NEXT SPRINT | V5-004 | Sidebar vs Page Title Mismatch (x3) | Medium | 1 hour |  |  | OPEN
Phase 2: NEXT SPRINT | V5-005 | Login Form Pre-filled with Test Data | Medium | 30 min |  |  | OPEN
Phase 2: NEXT SPRINT | V5-006 | Grid vs Pipeline View Inconsistency | Major | 2-3 hours |  |  | OPEN
Phase 2: NEXT SPRINT | V5-014 | Security Headers Partially Configured | Medium | 2-4 hours |  |  | OPEN
Phase 3: NEXT QUARTER | V5-007 | Time Format Inconsistency | Minor | 1 hour |  |  | OPEN
Phase 3: NEXT QUARTER | V5-008 | Credit Card Rate Format Mismatch | Minor | 30 min |  |  | OPEN
Phase 3: NEXT QUARTER | V5-009 | Staff Form Pre-filled with Sample Data | Minor | 15 min |  |  | OPEN
Phase 3: NEXT QUARTER | V5-015 | Sign Out Flow Needs Validation | Low | 1 hour |  |  | OPEN
Phase 4: FUTURE | V5-010 | Unhelpful Grid Empty State Message | Trivial | 30 min |  |  | OPEN
Phase 4: FUTURE | V5-011 | No Password Visibility Toggle | Trivial | 1 hour |  |  | OPEN

## Summary Dashboard
FLEXOLOGY V5 QA AUDIT - SUMMARY DASHBOARD
FINDINGS BY SEVERITY |  |  | FINDINGS BY PILLAR
Critical | 2 |  | Functional | 3
Major | 2 |  | UX | 6
Medium | 4 |  | Security | 3
Minor | 3 |  | Performance | 1
Trivial | 2 |  | Data Integrity | 1
Info | 2 |  | Accessibility | 1
TOTAL | 15
FINDINGS BY STATUS |  |  | VERIFICATION ACCURACY
OPEN | 13 |  | Verified | 2
VERIFIED | 2 |  | Partially | 5
|  |  | Not Verified | 2
|  |  | Regressed | 2
|  |  | New | 4
DEPLOYMENT READINESS
Score: | 5.8/10 | NOT READY (3 BLOCKERS remain)
Blockers:
• V5-001: POS System Returns 404
• V5-002: Revenue Data Mismatch
• V5-003: System Variables Page Scroll Bug