## All Findings
Finding ID | Category | Title | Severity | Priority | V6 Status | V7 Status | Description | Impact | Recommended Fix | Effort | Sprint
V7-001 | Performance | Homepage FCP 14.5s | Critical | P1 | 21.8s (FAIL) | 14.5s (IMPROVED but FAIL) | First Paint at 14,452ms. TTFB 553ms OK but client rendering blocked 14s. 33% better than V6 but 8x above 1.8s threshold. | Homepage unusable for 14+ seconds | Investigate GSAP/Framer-Motion blocking main thread. Check dynamic import effectiveness. Consider skeleton UI. | 8-16h | Sprint 1
V7-002 | Data Integrity | Revenue Data Mismatch | Critical | P1 | STILL BROKEN | STILL BROKEN (3rd cycle) | Gross Settled Revenue Rp 0 vs Outlet Leaderboard Rp 875,000 (475K + 400K) | Financial reporting unreliable, wrong business decisions | Audit Prisma totalPrice aggregation. Ensure KPI card and leaderboard use same data source. | 4-8h | Sprint 1
V7-003 | Security | Default Admin Credentials | Critical | P1 | STILL ACTIVE | STILL ACTIVE (3rd cycle) | 0000/admin grants full admin access. Dev claim of "rejection matrix" is false. | Full admin panel compromise | Actually block credentials in authActions.ts. Add env-based credential lockout. Force password change. | 2-4h | Sprint 1
V7-004 | Functionality | Booking Flow Selection Bug | High | P1 | Broken (Continue unresponsive) | PARTIALLY FIXED | Page loads, Step 1/5 renders with service options, but clicking In Studio/At-Home doesn't update state. Continue stays disabled=true. | Booking flow non-functional, zero revenue | Debug React state handler on service type buttons. Check if click event updates booking context state. | 4-6h | Sprint 1
V7-005 | UI/UX | Password Visibility Toggle | Medium | P3 | NOT IMPLEMENTED | STILL NOT IMPLEMENTED | No eye icon on registration password field. 0 toggle elements in DOM. | Users can't verify password input | Add Eye/EyeOff toggle component using lucide-react icons. | 2-3h | Sprint 3
V7-006 | Security | Missing Security Headers | High | P2 | Missing | STILL MISSING | CSP, X-Frame-Options, X-Content-Type-Options absent. | Clickjacking, injection, MIME sniffing risks | Add headers in next.config.js: headers() config or middleware.ts | 2-4h | Sprint 2
V7-007 | Functionality | POS Not in Admin Sidebar | Medium | P2 | Uncertain | NOT VISIBLE | No POS link in admin sidebar navigation | POS module may be inaccessible | Verify POS routes, add sidebar link | 2-4h | Sprint 2
V7-008 | UI/UX | Decimal Format Inconsistency | Low | P4 | Inconsistent | STILL INCONSISTENT | Credit Card Rate "0,02" vs label "0.029" — mixing comma/period | Minor data confusion | Standardize to period decimal separator | 1h | Sprint 3
V7-009 | Security | Weak XSS Sanitization | Medium | P2 | XSS found | PARTIALLY FIXED (weak) | Using replace(/[<>]/g, "") — strips angle brackets only. Bypasses possible. | XSS vulnerability remains | Use DOMPurify or server-side sanitization library | 3-4h | Sprint 2
V7-010 | Security | No Login Rate Limiting | High | P2 | Not tested | STILL ABSENT | No rate limiting on auth endpoint | Brute force attacks possible | Implement per-IP rate limiting: 5 attempts per 5 minutes | 4-6h | Sprint 2

## Quick Wins
Finding ID | Category | Title | Severity | Priority | V6 Status | V7 Status | Description | Impact | Recommended Fix | Effort | Sprint
V7-003 | Security | Default Admin Credentials | Critical | P1 | STILL ACTIVE | STILL ACTIVE (3rd cycle) | 0000/admin grants full admin access. Dev claim of "rejection matrix" is false. | Full admin panel compromise | Actually block credentials in authActions.ts. Add env-based credential lockout. Force password change. | 2-4h | Sprint 1
V7-005 | UI/UX | Password Visibility Toggle | Medium | P3 | NOT IMPLEMENTED | STILL NOT IMPLEMENTED | No eye icon on registration password field. 0 toggle elements in DOM. | Users can't verify password input | Add Eye/EyeOff toggle component using lucide-react icons. | 2-3h | Sprint 3
V7-008 | UI/UX | Decimal Format Inconsistency | Low | P4 | Inconsistent | STILL INCONSISTENT | Credit Card Rate "0,02" vs label "0.029" — mixing comma/period | Minor data confusion | Standardize to period decimal separator | 1h | Sprint 3

## Improvement Roadmap
Sprint | Focus Area | Findings | Priority Items | Estimated Effort | Target Metrics
Sprint 1 | Critical Blockers | V7-001, V7-002, V7-003, V7-004 | FCP, Revenue, Auth, Booking | 20-34h | Deployment readiness 40%
Sprint 2 | Security & Headers | V7-006, V7-009, V7-010, SEC-002→007 | CSP, Rate Limit, XSS, Cookies | 18-28h | Security score 50%
Sprint 3 | UI Polish & Minor Fixes | V7-005, V7-008 | Password Toggle, Decimals | 3-4h | UI consistency 90%
Sprint 4 | Performance & Monitoring | Continuous monitoring, CWV optimization | Load testing, error tracking | Ongoing | FCP <3s target

## Summary Dashboard
Flexology V7 Audit Summary
Deployment Score | 4.5/10
Total Findings | 10
Critical Issues | 3
High Priority | 4
Severity Distribution
Severity | Count | Percentage
Critical | 3 | 30%
High | 4 | 40%
Medium | 2 | 20%
Low | 1 | 10%

## V5-V6-V7 Trend
Metric | V5 (5.8/10) | V6 (3.2/10) | V7 (4.5/10) | Trend
Functionality | 4 | 2 | 4 | Recovery
Performance | 5 | 3 | 4 | Improving
Security | 4 | 3 | 3 | Stagnant
UI/UX | 5 | 4 | 6 | Improving
Data Integrity | 3 | 2 | 2 | Stagnant