## Security Findings
ID | Category | Title | Severity | OWASP | V6 Status | V7 Status | Description | PoC | Remediation | Effort | Sprint
SEC-001 | Authentication | Default Admin Credentials | Critical | A07 | STILL ACTIVE | STILL ACTIVE | 0000/admin grants full access | Login at /login with 0000/admin | Block in authActions.ts, force password change | 2-4h | Sprint 1
SEC-002 | Security Config | Missing CSP Header | Critical | A05 | MISSING | STILL MISSING | No Content-Security-Policy | curl -I check | Add CSP in next.config.js headers() | 2h | Sprint 2
SEC-003 | Security Config | Missing X-Frame-Options | High | A05 | MISSING | STILL MISSING | Clickjacking risk | curl -I check | Add X-Frame-Options: DENY | 30min | Sprint 2
SEC-004 | Injection | Weak XSS Sanitization | Medium | A03 | XSS present | PARTIALLY FIXED | Regex replace strips <> only, bypasses possible | Test with event handlers, encoding | Use DOMPurify | 3-4h | Sprint 2
SEC-005 | Auth | No Rate Limiting | High | A07 | Not tested | ABSENT | No throttling on login | 10 rapid failed logins — no block | Implement per-IP rate limiting | 4-6h | Sprint 2
SEC-006 | Session | Cookie Security Flags | High | A07 | Not tested | NEEDS TESTING | HttpOnly, Secure, SameSite flags unverified | Check DevTools Application > Cookies | Set all flags on flex_session | 1-2h | Sprint 2
SEC-007 | Security Config | Missing X-Content-Type-Options | Medium | A05 | MISSING | STILL MISSING | MIME sniffing risk | curl -I check | Add X-Content-Type-Options: nosniff | 30min | Sprint 2
SEC-008 | Access Control | POS Module Access Unclear | Medium | A01 | Uncertain | NOT IN SIDEBAR | POS not visible in admin navigation | Check admin sidebar — no POS link | Verify POS routes, add sidebar entry | 2-4h | Sprint 2

## OWASP Top 10 Checklist
OWASP Category | Description | V7 Status | Associated Finding
A01:2021 - Broken Access Control | Insufficient access control checks | FAIL | SEC-008 (POS not accessible)
A02:2021 - Cryptographic Failures | Weak encryption/transmission | PASS | None identified
A03:2021 - Injection | Code/SQL injection risks | PARTIAL | SEC-004 (Weak XSS sanitization)
A04:2021 - Insecure Design | Missing security by design | FAIL | Multiple header/config issues
A05:2021 - Security Misconfiguration | Misconfigured headers/settings | FAIL | SEC-002, SEC-003, SEC-007
A06:2021 - Vulnerable Components | Outdated dependencies | NEEDS TEST | Dependency audit required
A07:2021 - Auth & Session Mgmt | Weak authentication/session handling | FAIL | SEC-001, SEC-005, SEC-006
A08:2021 - Software Data Integrity | Insecure updates/CI/CD | WARN | No automated security tests
A09:2021 - Logging & Monitoring | Insufficient logging | NEEDS TEST | Security event logging audit
A10:2021 - SSRF | Server-side request forgery | PASS | None identified

## Remediation Roadmap
Phase | Category | Findings | Action Items | Target Sprint | Effort
BLOCKER | Authentication | SEC-001 | Disable 0000/admin, force password change | Sprint 1 | 2-4h
BLOCKER | Headers | SEC-002, SEC-003, SEC-007 | Implement CSP, X-Frame-Options, X-Content-Type-Options | Sprint 2 | 2-4h
HIGH | Auth Security | SEC-005 | Implement rate limiting per IP | Sprint 2 | 4-6h
HIGH | Session Security | SEC-006 | Set HttpOnly, Secure, SameSite on cookies | Sprint 2 | 1-2h
MEDIUM | Injection Prevention | SEC-004 | Replace regex with DOMPurify | Sprint 2 | 3-4h
MEDIUM | Access Control | SEC-008 | Verify POS routes, update sidebar | Sprint 2 | 2-4h
HARDENING | Testing | All | Add security-focused unit & integration tests | Sprint 3 | 8-12h
HARDENING | Monitoring | All | Set up security event logging & alerting | Sprint 4 | Ongoing

## Summary
Flexology V7 Security Audit Summary
Total Security Findings | 8
Critical Issues | 2
High Priority | 3
Medium Priority | 3
Deployment Blockers | 3
OWASP Coverage
Verified | 2
Partial | 1
Fail | 4
Not Tested | 3