## All Findings
ID | Category | Title | Severity | OWASP | Status | V5/V6/V7/V8 Trend | Description | Recommendation
V8-001 | Performance | Homepage FCP 48.6s (REGRESSED from V7 14.5s) | CRITICAL | — | OPEN | V5:21.8s→V6:21.8s→V7:14.5s→V8:48.6s | TTFB 2760ms + client-side JS blocking. DynamicLandingPageUI wrapper insufficient. GSAP/Framer-Motion still evaluated synchronously. | Implement static shell SSR, lazy-load all animation libs after first paint
V8-002 | Data Integrity | Revenue Dashboard Mismatch Rp 0 vs Rp 875,000 | CRITICAL | — | OPEN | V5:FAIL→V6:FAIL→V7:FAIL→V8:FAIL | KPI shows Rp 0, leaderboard shows Rp 475K + Rp 400K = Rp 875K. 4th cycle unfixed. | Refactor aggregation to use same query source as leaderboard
V8-003 | Security | Default Credentials 0000/admin Active | CRITICAL | A07 | OPEN | V5:FAIL→V6:FAIL→V7:FAIL→V8:FAIL | Login with 0000/admin grants full admin. Claimed "deleteMany DB purge" — FALSE. 4th cycle unfixed. | Block at authActions.ts + delete seed user from production DB
V8-004 | Functional | Booking Flow Selection — Invisible Feedback | HIGH | — | PARTIAL | V5:BROKEN→V6:BROKEN→V7:BROKEN→V8:PARTIAL | Service type buttons now advance to Step 2 (IMPROVED from V7 where Continue stayed disabled), but NO visual selection indicator. Users can't tell what they selected. | Add visual selected state (border, background change, checkmark)
V8-005 | Security | Missing Security Headers (CSP, X-Frame-Options, X-Content-Type-Options) | HIGH | A05 | OPEN | V6:FAIL→V7:FAIL→V8:FAIL | Only HSTS present. CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy all MISSING. Claimed headers in next.config.ts — FALSE. | Add headers in next.config.ts headers() function
V8-006 | Security | Weak XSS Sanitization | HIGH | A03 | OPEN | V7:FAIL→V8:FAIL | Registration form accepts <script>alert('xss')</script> without sanitization. Claimed isomorphic-dompurify — NOT verified on frontend. | Implement server-side DOMPurify on all form submissions
V8-007 | Security | No Login Rate Limiting | HIGH | A07 | OPEN | V7:FAIL→V8:FAIL | No rate limit headers in responses. Claimed rate-limiter-flexible — no evidence in HTTP responses. | Implement rate-limiter-flexible with X-RateLimit headers
V8-008 | UX | No Password Visibility Toggle | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Login and registration forms have no eye icon. Claimed PasswordInput.tsx — NOT deployed. | Create and deploy PasswordInput component with toggle
V8-009 | Navigation | POS Not in Admin Sidebar | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Sidebar: Dashboard, Bookings Pipeline, Staff Registry, Outlets & Managers, System Variables. No POS link. | Add POS Terminal link to sidebar navigation array
V8-010 | Data Display | Decimal Format Inconsistency | LOW | — | OPEN | V7:FAIL→V8:FAIL | Credit Card Rate field shows "0,02" (comma). Leaderboard uses "Rp 475,000" (comma thousands). Mixed locale formatting. | Centralize formatCurrency() using Intl.NumberFormat('id-ID')
V8-011 | Security | Cookie HttpOnly Flag — FIXED | LOW | A02 | FIXED | V7:FAIL→V8:PASS | flex_session cookie now has HttpOnly flag. document.cookie returns empty. | Verified fixed
V8-012 | Session | Admin Session Persistence Failure | HIGH | — | NEW | —→V8:FAIL | Navigating to /admin/bookings via URL bar drops session and redirects to homepage. Session only persists via sidebar link clicks. | Fix middleware.ts JWT verification for direct URL navigation

## V5-V8 Trend
Finding ID | V5 | V6 | V7 | V8
V8-001 | 21.8s | 21.8s | 14.5s | 48.6s
V8-002 | FAIL | FAIL | FAIL | FAIL
V8-003 | FAIL | FAIL | FAIL | FAIL
V8-004 | BROKEN | BROKEN | BROKEN | PARTIAL
V8-005 | N/A | FAIL | FAIL | FAIL
V8-006 | N/A | N/A | FAIL | FAIL
V8-007 | N/A | N/A | FAIL | FAIL
V8-008 | N/A | N/A | FAIL | FAIL
V8-009 | N/A | N/A | FAIL | FAIL
V8-010 | N/A | N/A | FAIL | FAIL
V8-011 | N/A | N/A | FAIL | PASS
V8-012 | N/A | N/A | N/A | FAIL

## Quick Wins
ID | Category | Title | Severity | OWASP | Status | V5/V6/V7/V8 Trend | Description | Recommendation
V8-008 | UX | No Password Visibility Toggle | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Login and registration forms have no eye icon. Claimed PasswordInput.tsx — NOT deployed. | Create and deploy PasswordInput component with toggle
V8-009 | Navigation | POS Not in Admin Sidebar | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Sidebar: Dashboard, Bookings Pipeline, Staff Registry, Outlets & Managers, System Variables. No POS link. | Add POS Terminal link to sidebar navigation array
V8-010 | Data Display | Decimal Format Inconsistency | LOW | — | OPEN | V7:FAIL→V8:FAIL | Credit Card Rate field shows "0,02" (comma). Leaderboard uses "Rp 475,000" (comma thousands). Mixed locale formatting. | Centralize formatCurrency() using Intl.NumberFormat('id-ID')
V8-011 | Security | Cookie HttpOnly Flag — FIXED | LOW | A02 | FIXED | V7:FAIL→V8:PASS | flex_session cookie now has HttpOnly flag. document.cookie returns empty. | Verified fixed

## Improvement Roadmap
Phase 1: Immediate (Security Critical)
ID | Category | Title | Severity | OWASP | Status | V5/V6/V7/V8 Trend | Description | Recommendation
V8-003 | Security | Default Credentials 0000/admin Active | CRITICAL | A07 | OPEN | V5:FAIL→V6:FAIL→V7:FAIL→V8:FAIL | Login with 0000/admin grants full admin. Claimed "deleteMany DB purge" — FALSE. 4th cycle unfixed. | Block at authActions.ts + delete seed user from production DB
V8-005 | Security | Missing Security Headers (CSP, X-Frame-Options, X-Content-Type-Options) | HIGH | A05 | OPEN | V6:FAIL→V7:FAIL→V8:FAIL | Only HSTS present. CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy all MISSING. Claimed headers in next.config.ts — FALSE. | Add headers in next.config.ts headers() function
V8-007 | Security | No Login Rate Limiting | HIGH | A07 | OPEN | V7:FAIL→V8:FAIL | No rate limit headers in responses. Claimed rate-limiter-flexible — no evidence in HTTP responses. | Implement rate-limiter-flexible with X-RateLimit headers
Phase 2: Sprint (High Priority)
ID | Category | Title | Severity | OWASP | Status | V5/V6/V7/V8 Trend | Description | Recommendation
V8-001 | Performance | Homepage FCP 48.6s (REGRESSED from V7 14.5s) | CRITICAL | — | OPEN | V5:21.8s→V6:21.8s→V7:14.5s→V8:48.6s | TTFB 2760ms + client-side JS blocking. DynamicLandingPageUI wrapper insufficient. GSAP/Framer-Motion still evaluated synchronously. | Implement static shell SSR, lazy-load all animation libs after first paint
V8-002 | Data Integrity | Revenue Dashboard Mismatch Rp 0 vs Rp 875,000 | CRITICAL | — | OPEN | V5:FAIL→V6:FAIL→V7:FAIL→V8:FAIL | KPI shows Rp 0, leaderboard shows Rp 475K + Rp 400K = Rp 875K. 4th cycle unfixed. | Refactor aggregation to use same query source as leaderboard
V8-006 | Security | Weak XSS Sanitization | HIGH | A03 | OPEN | V7:FAIL→V8:FAIL | Registration form accepts <script>alert('xss')</script> without sanitization. Claimed isomorphic-dompurify — NOT verified on frontend. | Implement server-side DOMPurify on all form submissions
V8-012 | Session | Admin Session Persistence Failure | HIGH | — | NEW | —→V8:FAIL | Navigating to /admin/bookings via URL bar drops session and redirects to homepage. Session only persists via sidebar link clicks. | Fix middleware.ts JWT verification for direct URL navigation
Phase 3: Polish (Medium Priority)
ID | Category | Title | Severity | OWASP | Status | V5/V6/V7/V8 Trend | Description | Recommendation
V8-004 | Functional | Booking Flow Selection — Invisible Feedback | HIGH | — | PARTIAL | V5:BROKEN→V6:BROKEN→V7:BROKEN→V8:PARTIAL | Service type buttons now advance to Step 2 (IMPROVED from V7 where Continue stayed disabled), but NO visual selection indicator. Users can't tell what they selected. | Add visual selected state (border, background change, checkmark)
V8-008 | UX | No Password Visibility Toggle | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Login and registration forms have no eye icon. Claimed PasswordInput.tsx — NOT deployed. | Create and deploy PasswordInput component with toggle
V8-009 | Navigation | POS Not in Admin Sidebar | MEDIUM | — | OPEN | V7:FAIL→V8:FAIL | Sidebar: Dashboard, Bookings Pipeline, Staff Registry, Outlets & Managers, System Variables. No POS link. | Add POS Terminal link to sidebar navigation array
V8-010 | Data Display | Decimal Format Inconsistency | LOW | — | OPEN | V7:FAIL→V8:FAIL | Credit Card Rate field shows "0,02" (comma). Leaderboard uses "Rp 475,000" (comma thousands). Mixed locale formatting. | Centralize formatCurrency() using Intl.NumberFormat('id-ID')

## Summary Dashboard
FLEXOLOGY V8 QA AUDIT - SUMMARY DASHBOARD
Overall Score | 3.8/10
SEVERITY BREAKDOWN
CRITICAL | 3
HIGH | 5
MEDIUM | 2
LOW | 2
STATUS BREAKDOWN
OPEN | 9
PARTIAL | 1
NEW | 1
FIXED | 1
CATEGORY BREAKDOWN
Data Display | 1
Data Integrity | 1
Functional | 1
Navigation | 1
Performance | 1
Security | 5
Session | 1
UX | 1